## Ringkasan
KodeKantor — WBS Pembagian Kerja Full Agentic
Sumber: PRD KodeKantor v1.0 (21 Okt 2026) · Rancangan: docs/ARCHITECTURE.md & DECISIONS.md · Snapshot 21 Okt 2026
Status program
Rancangan (Phase 0) selesai disusun & direview independen; penguncian formal menunggu gate G0 (keputusan PO). Implementasi Wave 1–2 sempat berjalan lalu DIHENTIKAN atas instruksi Product Owner; kode tersimpan sebagai snapshot yang belum diintegrasikan end-to-end. Tidak ada klaim MVP selesai.
Metrik | Nilai | Keterangan
Jumlah work package | 137 | Semua phase 0–16
WP Selesai | 12 | Terverifikasi
WP Snapshot (belum terintegrasi) | 11 | Kode + test unit/integrasi lulus
WP Sebagian | 12 | Ada gap tercatat
WP Belum | 102 | Termasuk gate manusia
Progres (Selesai+Snapshot) / total | 16.79% | Bukan % fitur jadi; ukuran WP
Agent AI (aktual + rencana) | 22 | AG-00..AG-21
Peran manusia | 2 | Product Owner, Operator
Token aktual subagent terukur (juta) | 6.345 | Dari laporan harness
Durasi aktual subagent terukur (menit, kumulatif) | 636.8 | Paralel: wall-clock jauh lebih pendek
Estimasi token WP 'Belum' (juta) [Menebak] | 50.85 | Kalibrasi dari aktual
Estimasi jam agent WP 'Belum' [Menebak] | 138.6 | Termasuk aktivitas manusia
AC dengan test di snapshot | 17 | Dari 20 AC
AC sebagian | 3 | AC-15, AC-19, AC-20
Cara pakai
Agent Roster | Peran, kepemilikan file (anti konflik paralel), izin, input/output, reviewer, pemakaian aktual.
WBS | Work package per phase/wave dengan dependensi, FR/AC, status & bukti. Ubah status lewat daftar pilihan.
Timeline | Matriks wave × agent otomatis dari WBS.
RACI | Akuntabilitas; kolom 'Jumlah A' harus 1 per aktivitas.
Traceability AC | AC → FR → WP pembangun → WP verifikasi.
Status Modul / Gates / Risiko | Ringkasan modul M01–M20, gate persetujuan manusia, risiko & mitigasi.
Aturan kerja agent | Path milik tegas; tanpa git write (hanya AG-00 commit); kontrak berubah → ADR; tidak boleh klaim test lulus tanpa output; gate manusia tidak dapat dilewati.
Label keyakinan | Angka aktual = [Pasti] (diukur). Estimasi WP 'Belum' = [Menebak].

## Agent Roster
Agent Roster
Siapa mengerjakan apa. Aktual = pemakaian nyata subagent pada Wave 1–2 (dari laporan harness). Kosong = belum berjalan / tidak terukur.
ID | Peran | Jenis | Model / tier rekomendasi | Tanggung jawab | Path milik (kepemilikan file) | Izin & batasan | Input | Output | Direview oleh | Wave aktif | Status | Aktual token (juta) | Aktual durasi (menit) | Tool calls
AG-00 | Lead Architect / Orchestrator | AI agent (sesi utama) | Opus (complex) | Analisis PRD, kontrak arsitektur, ADR, pemecahan WP, brief agent, verifikasi output, integrasi, commit tunggal | docs/{ARCHITECTURE,DATA_MODEL,API_CONTRACTS,DECISIONS,TOOL_CATALOG,CONFIGURATION,IMPLEMENTATION_TRACKER}.md, CLAUDE.md, file kontrak (agents/contracts.py, llm/base.py, tools/base.py, sandbox/client.py) | Satu-satunya yang boleh git commit/merge; mengubah core/models/kontrak | PRD, laporan agent, hasil test | Kontrak terkunci, ADR, tracker, keputusan integrasi | Product Owner (gate) | W0–W6 | Aktif
AG-01 | Backend Core | AI agent | Opus/Sonnet (default) | Config fail-fast, DB & 28 tabel + migrasi, error envelope, logging+redaksi, RBAC, auth/sesi/CSRF, events, audit, state machine, Celery app, fixture test bersama | backend/pyproject, alembic/, app/{main,cli}.py, app/core/, app/models/, app/api/{deps,router}.py, routes auth/health, services auth/users, workflow/states.py, worker/celery_app.py, tests/conftest.py | Tulis hanya path milik; tanpa git write | ARCHITECTURE, DATA_MODEL, API_CONTRACTS, CONFIGURATION | Fondasi backend + 417 test | AG-00 | W1, W3 | Selesai (snapshot) | 0.446 | 42.8 | 164
AG-02 | Workspace & Git | AI agent | Sonnet (default) | Safe path, filesystem & patch atomik, import arsip aman, stack detection, template project, GitAdapter ter-hardening | app/workspace/{paths,fs,patches,archive,stack,templates_registry,templates/}, app/gitops/ | Tulis hanya path milik; repo git sementara di /tmp | ARCHITECTURE §7, SECURITY_MODEL | Workspace & Git API + 316 test | AG-00, AG-13 | W1 | Selesai (snapshot) | 0.419 | 44.4 | 110
AG-03 | Sandbox & Runtime | AI agent | Sonnet (default) | Sandbox-manager (profil tetap), image sandbox Python/Node, klien HTTP backend, hardening (.git mask, no auto-pull, socket-proxy) | sandbox_manager/, sandbox-images/, app/sandbox/{http_client,profiles,junit,factory}.py | Boleh akses Docker daemon lokal untuk test; tanpa git write | API_CONTRACTS §10, TOOL_CATALOG, ADR-009 | Service sandbox + 207 unit + 23 test Docker nyata | AG-00, AG-13 | W1 (+hardening) | Selesai | 0.346 | 34.3 | 102
AG-04 | Frontend Foundation | AI agent | Sonnet (default) | Scaffold React/Vite/TS, design tokens KodeKantor, UI kit Radix, API client + SSE, i18n, auth, dashboard, projects, agents, approvals | frontend/ (kecuali feature folder milik AG-10/AG-11) | Tanpa git write | API_CONTRACTS, PRD §4 | Shell aplikasi + 93 test | AG-00 | W1 | Selesai (snapshot) | 0.461 | 55.8 | 144
AG-05 | Docs & Catalog | AI agent | Sonnet (default) | PRD.md, FR_CATALOG (159 FR), registry 42 agent + validator, AGENT_CATALOG, SECURITY_MODEL, USER_PROXY_ACCEPTANCE, TEST_STRATEGY, ROADMAP | docs/{PRD,FR_CATALOG,AGENT_CATALOG,SECURITY_MODEL,USER_PROXY_ACCEPTANCE,TEST_STRATEGY,IMPLEMENTATION_ROADMAP}.md, agents/, scripts/validate_registry.py | Tanpa git write | PRD lengkap, kontrak | Traceability & katalog | AG-00, PO | W1 | Selesai | 0.433 | 35.5 | 60
AG-06 | Infra & DevOps | AI agent | Sonnet (default) | Compose 11 service, Caddy, docker-socket-proxy, egress proxy, Dockerfile, CI (lint/test/security/e2e/sbom), backup/restore, runbook | infra/, .env.example, Makefile, .github/, backend/Dockerfile, frontend/Dockerfile, scripts/*.sh, docs/{RUNBOOK,DEPLOYMENT}.md, README.md | Boleh build/run container lokal; tanpa git write | ARCHITECTURE §2/§12, CONFIGURATION | Topologi deploy tervalidasi | AG-00, AG-13 | W1, W5 | Selesai (snapshot) | 0.389 | 50.1 | 142
AG-07 | Agentic Core | AI agent | Opus (complex) | Adapter Claude (streaming, retry, cache, error mapping), ScriptedProvider + skenario, Tool Gateway & policy, builtin tools, agent runtime & prompt, approvals, budget, usage, settings | app/llm/*, app/tools/*, app/agents/{registry,runtime,factory,prompting,prompts/}, workflow/budget.py, services+routes approvals/usage/agents/settings | Tanpa git write; tanpa API key nyata | TOOL_CATALOG, contracts.py, PRD §7.3 | Runtime agent + 201 test | AG-00, AG-13 | W2, W3 | Selesai (snapshot) | 0.734 | 72.8 | 203
AG-08 | Workflow & Acceptance | AI agent | Opus (complex) | Orchestrator S1–S10, lease/checkpoint/recovery/cancel, SSE, chat, test runner, review, User Proxy evidence verification, gate, remediasi, deployments P2 | app/workflow/{engine,steps,lease,recovery,dispatch,context,checkpoint,gate,approval_handlers}.py, worker/jobs.py, services+routes tasks/conversations/events/testing/terminal/reviews/acceptance/artifacts/deployments | Tanpa git write | ARCHITECTURE §5, USER_PROXY_ACCEPTANCE | Engine workflow + 178 test | AG-00, AG-13 | W2, W3 | Selesai (snapshot) | 0.7 | 70.2 | 161
AG-09 | Platform Services | AI agent | Sonnet (default) | Projects & import, workspace/git API, search & index, knowledge, dashboard, admin & policies, audit query | app/workspace/{search,symbols}.py, services+routes projects/workspace/git/repository/indexing/knowledge/dashboard/admin/audit, worker/platform_jobs.py | Tanpa git write | API_CONTRACTS §3/§4/§9 | Layanan platform + 131 test | AG-00 | W2, W3 | Selesai (snapshot) | 0.594 | 56.2 | 161
AG-10 | Frontend Workspace | AI agent | Sonnet (default) | IDE (explorer, Monaco, chat, terminal read-only), task detail & plan, diff review, testing, User Proxy validation, preview | frontend/src/features/{workspace,tasks,review,testing,acceptance,preview}, hooks terkait | Tanpa git write | API_CONTRACTS §4/§5/§7/§8, PRD §4 | Layar inti + 77 test | AG-00 | W2, W3 | Selesai (snapshot) | 0.628 | 76.2 | 202
AG-11 | Frontend Admin | AI agent | Sonnet (default) | Settings provider (tanpa input API key), usage & budget, users, policies, audit, knowledge, deployments | frontend/src/features/{settings,admin,knowledge,deployments}, hooks terkait | Tanpa git write | API_CONTRACTS §9, ADR-004/011 | Layar admin + 81 test | AG-00 | W2, W3 | Selesai (snapshot) | 0.453 | 45.1 | 150
AG-12 | Integration & E2E QA | AI agent (rencana) | Opus (complex) | Stack penuh dengan scripted provider, Playwright happy path & remediasi, clean-install smoke, perbaikan integrasi via brief Lead | tests/e2e/, CI job e2e/clean-install | Tanpa git write; lingkungan Docker | Snapshot kode, TEST_STRATEGY | Bukti E2E AC-01..AC-20 | AG-00, PO | W3–W4 | Belum dimulai
AG-13 | Security Reviewer | AI agent (rencana) | Opus (complex) | Review independen read-only, test keamanan (path, symlink, prompt injection, approval replay, limit container, secret leak), sign-off 🔒 | backend/tests/security/ (bersama QA); selain itu read-only | Read-only kecuali test keamanan | SECURITY_MODEL, diff per WP | Laporan & sign-off keamanan | PO | W3–W5 | Belum dimulai
AG-14 | Release & Staging | AI agent (rencana) | Sonnet (default) | Deploy staging VPS, drill backup/restore, gVisor, smoke, rollback rehearsal — bersama Operator manusia | infra/ (bersama AG-06), docs/RUNBOOK.md | Akses VPS staging via Operator; tidak ke production | RUNBOOK, DEPLOYMENT | Staging teruji | Operator, PO | W5 | Belum dimulai
AG-15 | Specialist Rollout | AI agent (rencana) | Sonnet/Opus per agent | Aktivasi 22 agent planned per wave: prompt, kontrak, eval set, contract test, ukur manfaat | agents/registry.yaml (enable), app/agents/prompts/, eval set | Tanpa git write | AGENT_CATALOG, metrik pilot | Specialist aktif terukur | AG-00, PO | W6 | Belum dimulai
AG-16 | Design Reviewer (independen) | AI agent | Opus (complex) | Review adversarial rancangan vs PRD: cakupan, konsistensi, kualitas WBS, keamanan desain | – (read-only) | Read-only; tidak boleh mengubah file | Seluruh paket desain + workbook WBS | Daftar temuan bertingkat severity | AG-00 | W2 | Selesai | 0.333 | 8.7 | 33
AG-17 | Demo & Prototype UI | AI agent | Opus (complex) | Merekam eksekusi nyata dan membangun live demo replay + prototipe modul perluasan berlabel | /home/claude/kodekantor-demo/ (template.html, build.py, test_replay.py) | Tanpa git write; tidak boleh mengarang data | demo_data.json dari rekaman nyata, PLATFORM_EXPANSION.md | Artifact KodeKantor Replay | AG-00 | W3 | Selesai | 0.409 | 44.7 | 65
AG-18 | Integrations Engineer (GitHub) | AI agent (rencana) | Opus (complex) | GitHub App: instalasi, callback, webhook HMAC, token per operasi, import/pull repo privat, push branch & PR via R3 | backend/app/integrations/github/, routes integrations, tabel github_* | Tanpa git write; private key hanya di container worker-integrations (ADR-053) | ADR-041, PLATFORM_EXPANSION §5; ADR-067 (WP-6.10) | Integrasi GitHub teruji; klien Admin API rekonsiliasi | AG-00, AG-13 | W5 (WP-6.10), W7 | Belum dimulai
AG-19 | AI Portal Backend | AI agent (rencana) | Opus (complex) | Assistant service: thread/stream, riset web bersitasi, engine dokumen, ImageProvider, KB leksikal (FTS + pg_trgm, ADR-046), analisis data | backend/app/assistant/, llm/image_*, docengine/, kb/ | Tanpa git write | ADR-037..040, 044, 046, 047 | Portal AI backend + test kontrak provider; biaya capability ke monitoring (WP-10.7) | AG-00, AG-13 | W8–W9 | Belum dimulai
AG-20 | AI Portal Frontend | AI agent (rencana) | Sonnet (default) | UI Portal AI: chat, panel sitasi, pembuat dokumen, galeri gambar, KB, capability & kuota | frontend/src/features/assistant/** | Tanpa git write | API Portal AI | Layar Portal AI + test | AG-00, AG-12 | W8–W9 | Belum dimulai
AG-21 | Portfolio Full-stack | AI agent (rencana) | Sonnet (default) | Portal Portfolio: model konten, impor GitHub/KodeKantor, CV DOCX/PDF, asisten lamaran, situs publik + publish R3 | backend/app/portfolio/, frontend/src/features/portfolio/** | Tanpa git write; AI hanya draft | ADR-042 | Portal Portfolio teruji | AG-00, AG-13 | W10 | Belum dimulai
PO | Product Owner (Tira) | Manusia | – | Putuskan ADR Proposed, review FR turunan, setujui exit phase & gate, pilih P1, setujui aktivasi agent | – | Otoritas persetujuan akhir; di pilot single-owner praktis satu-satunya pemutus approval (formal: izin per action_type, API §11.1) | Laporan Lead, tracker | Keputusan gate | – | Semua gate | Aktif
OPS | Operator VPS | Manusia | – | VPS, secret (API key Claude, token sandbox), model ID & budget, backup/restore drill, rotasi kunci | Server & secret store | Akses produksi/staging | RUNBOOK | Lingkungan siap & drill tercatat | PO | W3 (readiness gate), W5 | Belum dimulai
Total | [11 empty] | 6.345 | 636.8 | 1697
Catatan: token aktual AG-03 belum termasuk sesi hardening lanjutan (tidak dilaporkan). AG-00 (sesi utama) tidak diukur per WP.

## WBS
WBS
Work breakdown agentik per phase PRD §13. Semua kolom estimasi = [Menebak] (untuk WP selesai tanpa aktual = perkiraan retrospektif), dikalibrasi dari aktual Wave 1–2 (~0,33–0,73 juta token & 9–76 menit per agent-run).
WP ID | Phase | Wave | Modul | Work package | Deliverable / scope | Owner (agent) | Reviewer / gate | Dependensi | FR | AC | Prioritas | Status | Bukti / evidence | Est. durasi agent (jam) | Est. token (juta) | Aktual token (juta) | Aktual durasi (menit) | Catatan
WP-0.1 | P0 Discovery & contracts | W0 | Semua | Review PRD & analisis gap | Temuan: FR-001..159 tidak didefinisikan; state machine tanpa running→cancelled; akses Docker sandbox-manager tidak diatur; 8 open decisions | AG-00 | PO | – | – | – | P0 | Selesai | DECISIONS ADR-006/009/020 | 0.5 | 0.1
WP-0.2 | P0 Discovery & contracts | W0 | Semua | Arsitektur sistem (C4, layering, interface inti) | ARCHITECTURE.md: container view, pemetaan M01–M20, aturan dependensi, interface LLMProvider/ToolGateway/AgentRuntime/SandboxClient/EventBus/GitAdapter, pipeline S1–S10, event, approval | AG-00 | PO | WP-0.1 | Semua | Semua | P0 | Selesai | docs/ARCHITECTURE.md | 1 | 0.15
WP-0.3 | P0 Discovery & contracts | W0 | Semua | Data model | DATA_MODEL.md: 24 entitas konseptual (→ 28 tabel), constraint, retensi | AG-00 | PO | WP-0.2 | Semua | AC-19 | P0 | Selesai | docs/DATA_MODEL.md | 0.5 | 0.05
WP-0.4 | P0 Discovery & contracts | W0 | Semua | Kontrak API + SSE + API sandbox internal | API_CONTRACTS.md §1–§10 (+ §11 v1.1) | AG-00 | PO | WP-0.2 | Semua | AC-05 | P0 | Selesai | docs/API_CONTRACTS.md | 0.75 | 0.08
WP-0.5 | P0 Discovery & contracts | W0 | Semua | ADR 001–020 (termasuk 8 open decisions) | DECISIONS.md: ADR-001..035; 9 Proposed menunggu PO | AG-00 | PO (G0) | WP-0.1 | – | – | P0 | Sebagian | docs/DECISIONS.md | 0.5 | 0.05 |  |  | 9 ADR Proposed perlu keputusan PO
WP-0.6 | P0 Discovery & contracts | W0 | M07, M09, M10, M17 | Kontrak tool, konfigurasi & I/O agent | TOOL_CATALOG.md, CONFIGURATION.md, agents/contracts.py, llm/base.py, tools/base.py, sandbox/client.py | AG-00 | AG-13 | WP-0.2 | FR-041–067 | AC-06 | P0 | Selesai | file kontrak di repo | 0.75 | 0.06
WP-0.7 | P0 Discovery & contracts | W1 | Semua | Katalog & traceability | FR_CATALOG (159 FR), registry 42 agent + validator, AGENT_CATALOG, SECURITY_MODEL, USER_PROXY_ACCEPTANCE, TEST_STRATEGY, ROADMAP | AG-05 | AG-00, PO | WP-0.2..0.6 | FR-001–159 | AC-01–20 | P0 | Sebagian | validate_registry: OK 42 agents; 17 test validator lulus | 0.6 | 0.43 | 0.433 | 35.5 | Draft selesai; FR turunan menunggu review PO (G0)
WP-0.8 | P0 Discovery & contracts | W2 | Semua | Finalisasi rancangan dari temuan Wave 1–2 | ADR-021..035, API v1.1 (§11–§11.3), peta route UI, roster aktual di ROADMAP, IMPLEMENTATION_TRACKER, tindak lanjut 11 temuan review | AG-00 | AG-16; PO (G0) | WP-1.1..1.5, WP-2.1, WP-3.1, WP-3.2, WP-5.2, WP-6.1, WP-0.11 | – | – | P0 | Selesai | docs/DECISIONS.md, docs/IMPLEMENTATION_TRACKER.md | 0.5 | 0.05
WP-0.10 | P0 Discovery & contracts | W2 | Semua | Peta route UI | ARCHITECTURE §3.1b: route ↔ layar PRD §4 ↔ modul | AG-00 | AG-16 | WP-0.4 | FR-007–159 (UI) | AC-03 | P0 | Selesai | docs/ARCHITECTURE.md §3.1b; frontend/src/app/routes.tsx | 0.2 | 0.02 |  |  | Estimasi retrospektif
WP-0.11 | P0 Discovery & contracts | W2 | Semua | Review desain independen | 11 temuan (4 High, 6 Medium, 1 Low) → semua ditindaklanjuti di dokumen & WBS | AG-16 | AG-00 | WP-0.2..0.7 | – | – | P0 | Selesai | Tracker §7 | 0.2 | 0.33 | 0.333 | 8.7
WP-0.9 | P0 Discovery & contracts | W3 | Semua | Gate G0: review PO atas FR turunan & ADR Proposed | Keputusan tertulis PO; ADR berubah status Accepted/Revised | PO | – | WP-0.7, WP-0.8 | FR-001–159 | – | P0 | Belum | – | 2 | 0 |  |  | Aktivitas manusia
WP-1.1 | P1 Foundation | W1 | M01, M08, M19 | Backend core | Config fail-fast, 28 tabel + migrasi, envelope/error, logging+redaksi, RBAC, auth/sesi/CSRF/lockout, events, audit append-only, state machine, Celery app, conftest | AG-01 | AG-00 | WP-0.2..0.6 | FR-001–006, FR-048, FR-144–148 | AC-01, AC-15, AC-19 | P0 | Snapshot (belum terintegrasi) | 417 test milik agent lulus; suite backend 1314 lulus/2 gagal (sinkronisasi dok) | 1 | 0.45 | 0.446 | 42.8
WP-1.2 | P1 Foundation | W1 | M03, M04, M05, M15 | Workspace & Git | Safe path, patch atomik, import arsip aman, stack detection, 6 template, GitAdapter ter-hardening | AG-02 | AG-00, AG-13 | WP-0.2 | FR-012–032, FR-113–116 | AC-02, AC-03, AC-09 | P0 | Snapshot (belum terintegrasi) | 316 test lulus; template lulus pytest/ruff offline | 1 | 0.42 | 0.419 | 44.4 | Temuan: .git/config → eksekusi host (dimitigasi)
WP-1.3 | P1 Foundation | W1 | M10, M11 | Sandbox manager + image + klien | Profil tetap, HostConfig dikunci server, image uid 10001, klien HTTP backend, junit/coverage parser | AG-03 | AG-00, AG-13 | WP-0.4, WP-0.6 | FR-068–083 | AC-07, AC-08 | P0 | Sebagian | 207 unit + 23 Docker nyata (dijalankan ulang Lead: 23 passed) | 0.8 | 0.35 | 0.346 | 34.3 | Menunggu sign-off 🔒 AG-13
WP-1.4 | P1 Foundation | W1 | M01, M02, M03, M07 | Frontend foundation | Scaffold, design tokens, UI kit, API client + SSE resume, i18n id/en, login, dashboard, projects, agents, approvals | AG-04 | AG-00 | WP-0.4 | FR-001–018, FR-041–047 | AC-01, AC-03 | P0 | Snapshot (belum terintegrasi) | 93 test, build OK | 1 | 0.46 | 0.461 | 55.8
WP-1.5 | P1 Foundation | W1 | Infra | Infra, CI & runbook | Compose 11 service + jaringan privat, Caddy, socket-proxy, egress proxy, CI keamanan, backup/restore, RUNBOOK | AG-06 | AG-00, AG-13 | WP-0.2 | FR-136–137, FR-149 | AC-20 | P0 | Snapshot (belum terintegrasi) | compose config, hadolint, shellcheck, actionlint, caddy validate, drill restore lulus | 0.9 | 0.39 | 0.389 | 50.1
WP-1.6 | P1 Foundation | W3 | Infra | Gate G1: clean install + health + migrasi + smoke | make up dari nol, semua service healthy, alembic head, smoke API | AG-12 | AG-00, PO (G1) | WP-1.1..1.5, WP-INT-01 | FR-149 | AC-20 | P0 | Belum | – | 1 | 0.3 |  |  | Perlu diulang setelah Wave 2
WP-2.1 | P2 Projects & IDE | W2 | M02–M05, M15, M16, M19, M20 | Platform services | Projects (blank/template/git_https/arsip), workspace & git API, search/index, knowledge, dashboard, admin, audit | AG-09 | AG-00 | WP-1.1, WP-1.2 | FR-007–032, FR-113–127, FR-152–159 | AC-01, AC-02, AC-03, AC-19 | P0 | Snapshot (belum terintegrasi) | 131 test lulus | 1 | 0.6 | 0.594 | 56.2 | FR-127 belum
WP-2.2 | P2 Projects & IDE | W2 | M05, M06, M11 | Frontend IDE | Explorer, Monaco lokal + save/version conflict, chat + streaming + cancel, terminal read-only | AG-10 | AG-00 | WP-1.4 | FR-026–040, FR-077–083 | AC-03, AC-05, AC-14 | P0 | Snapshot (belum terintegrasi) | bagian dari 77 test AG-10 | 0.6 | 0.3 |  |  | Aktual tercatat di WP-5.2
WP-3.1 | P3 First agent loop | W2 | M07, M09, M17 | Agentic core | Adapter Claude, ScriptedProvider (generic/calc/calc-debug/calc-gap), Tool Gateway + builtin tools, runtime, approvals, budget, usage, settings | AG-07 | AG-00, AG-13 | WP-1.1..1.3 | FR-041–067, FR-128–135 | AC-06, AC-13, AC-15, AC-16 | P0 | Snapshot (belum terintegrasi) | 201 test lulus; bug log SDK (prompt bocor di DEBUG) ditemukan & diperbaiki | 1.2 | 0.73 | 0.734 | 72.8
WP-3.2 | P3 First agent loop | W2 | M06, M08 | Workflow engine | Orchestrator S1–S10, dispatch, lease/heartbeat, checkpoint, recovery, cancel, SSE replay, chat→task | AG-08 | AG-00 | WP-3.1 | FR-033–040, FR-048–058 | AC-04, AC-05, AC-14, AC-17 | P0 | Sebagian | 178 test lulus termasuk 3 E2E level service via runtime nyata | 1.2 | 0.7 | 0.7 | 70.2 | Kurang 3 transisi state (ADR-021)
WP-4.1 | P4 Sandbox & tests | W2 | M12 | Test runner & debug loop | run_profile (status jujur), artefak junit/coverage, debugger C20 maks 5 percobaan | AG-08 | AG-00 | WP-1.3, WP-3.2 | FR-084–094 | AC-08 | P0 | Snapshot (belum terintegrasi) | termasuk dalam 178 test AG-08 | 0.5 | 0.2
WP-4.2 | P4 Sandbox & tests | W2 | M10 | Hardening sandbox lanjutan | .git disembunyikan, image tanpa auto-pull, flag socket-proxy minimum | AG-03 | AG-13 | WP-1.3 | FR-068–076 | AC-07 | P0 | Sebagian | 23 test Docker lulus via socket-proxy (laporan agent) | 0.5 | 0.15 |  |  | Estimasi retrospektif; menunggu sign-off 🔒
WP-4.3 | P4 Sandbox & tests | W4 | M10 | Gate G4 🔒: security gate sebelum egress internet | Review threat T1–T10, uji egress proxy allowlist, gVisor opsional | AG-13 | PO (G4) | WP-4.2, WP-SEC-01 | FR-068–076 | AC-07 | P0 | Belum | – | 1 | 0.4
WP-5.1 | P5 Review & User Proxy | W2 | M13, M14 | Review + User Proxy backend | Findings D22 + secret scan, verifikasi evidence (downgrade), gate S9, remediasi otomatis terbatas, waiver ter-audit | AG-08 | AG-00 | WP-3.2 | FR-095–112 | AC-10, AC-11, AC-12, AC-18 | P0 | Snapshot (belum terintegrasi) | skenario calc-gap lulus di level service | 0.6 | 0.25
WP-5.2 | P5 Review & User Proxy | W2 | M05, M06, M11–M14 | Frontend workflow screens | Task detail & plan, diff review, testing, User Proxy validation, preview (P1) | AG-10 | AG-00 | WP-1.4 | FR-095–112 | AC-09, AC-11, AC-12 | P0 | Snapshot (belum terintegrasi) | 77 test AG-10; total FE 259 lulus | 1.2 | 0.63 | 0.628 | 76.2
WP-6.1 | P6 Product completeness | W2 | M16–M20 | Frontend admin | Provider (tanpa input key), usage & budget, users, policies, audit, knowledge, deployments | AG-11 | AG-00 | WP-1.4 | FR-121–159 | AC-15, AC-16, AC-19 | P1 | Snapshot (belum terintegrasi) | 81 test lulus | 0.8 | 0.45 | 0.453 | 45.1
WP-INT-01 | P3–P5 Integrasi | W3 | M01, M08 | Sinkronisasi test↔dokumen | Tambah variabel CONFIGURATION ke Settings (TASK_MAX_ITERATIONS dll.), perbarui test Celery imports | AG-01 | AG-00 | WP-0.8, WP-0.9 | – | AC-20 | P0 | Belum | 2 test gagal saat ini | 0.3 | 0.1
WP-INT-02 | P3–P5 Integrasi | W3 | M08, M17 | ADR-021 & ADR-025 | Transisi state tambahan + test matriks; enum cost_status partial & agent_runs approval_required (migrasi 0002) | AG-01 | AG-00 | WP-INT-01 | FR-048–058, FR-131–134 | AC-14, AC-16 | P0 | Belum | – | 0.5 | 0.2
WP-INT-03 | P3–P5 Integrasi | W3 | M08, M09 | ADR-022 & ADR-024 (ports, handler approval) | WorkflowPorts/ToolPorts, hapus bypass importlib, kontrak import-linter, handler commit+retry, bootstrap handler di API & worker | AG-08 | AG-00, AG-13 | WP-INT-02 | FR-048–067 | AC-06, AC-13 | P0 | Sebagian | Handler approval kini terdaftar di proses API (commit 91e8e7d); suite backend 1316 lulus / 2 gagal lama | 1 | 0.4 |  |  | Sisa: WorkflowPorts/ToolPorts, hapus importlib, handler retry
WP-INT-04 | P3–P5 Integrasi | W3 | Semua | Kontrak API v1.1 (ADR-029) | Field/endpoint §11 di backend + penyesuaian hook frontend; delete project membatalkan task aktif | AG-08, AG-09 → AG-10, AG-11 | AG-00 | WP-INT-03 | Lintas modul | AC-04, AC-11, AC-16 | P0 | Belum | – | 1.5 | 0.8 |  |  | Backend dulu, lalu FE (2 sub-wave)
WP-INT-05 | P3–P5 Integrasi | W3 | M19 | Redaksi ADR-030 🔒 | Pola key=value huruf kecil + test negatif; uji kebocoran secret end-to-end di log/event/artefak/respons | AG-01 | AG-13 | WP-INT-01 | FR-002, FR-025, FR-144 | AC-15 | P0 | Belum | – | 0.4 | 0.15
WP-INT-06 | P3–P5 Integrasi | W3 | Infra | Stack penuh dengan scripted provider | make up, worker/scheduler sehat, handler approval terdaftar, demo calc berjalan lewat UI | AG-12 | AG-00 | WP-INT-01..05 | – | AC-20 | P0 | Sebagian | Stack dev tanpa compose (API, worker, sandbox Docker nyata) menjalankan calc, calc-debug, calc-gap sampai completed | 1 | 0.4 |  |  | Compose penuh belum dijalankan ulang
WP-INT-07 | P3–P5 Integrasi | W3 | M17 | Readiness gate Claude Platform API | API key & model ID nyata dari katalog resmi, claude-smoke lulus (streaming, usage, tool-use, cancel, secret tak bocor), harga diverifikasi | OPS + AG-07 | PO | WP-INT-06 | FR-128–135 | AC-15, AC-16 | P0 | Belum | – | 0.5 | 0.1 |  |  | Butuh secret dari Operator
WP-INT-08 | P3–P5 Integrasi | W3 | M08, M10, M12, M17 | ADR-031..035 | Pause & batas durasi, readiness gate mengikat, sandbox read-only untuk main + batas disk, matriks approval & izin baru, failure_kind | AG-08, AG-07, AG-03, AG-01 | AG-00, AG-13 | WP-INT-02 | FR-045, FR-057, FR-087, FR-132, FR-135 | AC-07, AC-13, AC-16 | P0 | Belum | – | 1.5 | 0.7
WP-E2E-01 | P5 Review & User Proxy | W4 | Semua | Playwright happy path | login → project → prompt → patch → test → diff → User Proxy → approve/reject | AG-12 | AG-00, PO | WP-INT-06, WP-INT-08 | Lintas modul | AC-01–AC-13 | P0 | Belum | – | 1.5 | 0.6
WP-E2E-02 | P5 Review & User Proxy | W4 | M08, M14 | Playwright remediasi, cancel, recovery | Skenario calc-gap (AC-18), cancel saat running (AC-14), restart worker (AC-17) | AG-12 | AG-00 | WP-E2E-01 | FR-053–057, FR-100–109 | AC-14, AC-17, AC-18 | P0 | Belum | – | 1 | 0.4
WP-E2E-03 | P5 Review & User Proxy | W4 | M19, Infra | Clean-install smoke & audit trace | Job CI clean-install; trace prompt→plan→agent run→tool call→artifact→test→acceptance | AG-12 | AG-00, PO (G3) | WP-E2E-01 | FR-143–148 | AC-19, AC-20 | P0 | Belum | – | 1 | 0.4
WP-SEC-01 | P4 Sandbox & tests | W4 | M09, M10, M01 | Review keamanan independen 🔒 | Fixture: path traversal/symlink, prompt injection repo, approval replay, limit container, cross-project, secret leak; sign-off tertulis | AG-13 | PO | WP-INT-03, WP-INT-05 | FR-059–076 | AC-01, AC-06, AC-07, AC-13, AC-15 | P0 | Belum | – | 1.5 | 0.6
WP-G2 | P2 Projects & IDE | W4 | M02–M05 | Gate G2: exit Projects & IDE | User dapat membuka project dan view/edit file; uji otorisasi lulus di stack penuh | PO | – | WP-2.1, WP-2.2, WP-INT-06 | – | AC-01–AC-03 | P0 | Belum | – | 0.5 | 0 |  |  | Aktivitas manusia
WP-G5 | P5 Review & User Proxy | W4 | M13, M14 | Gate G5: exit Review & User Proxy | E2E membuktikan requirement gagal → perbaikan → revalidasi | PO | – | WP-E2E-02 | FR-095–112 | AC-11, AC-12, AC-18 | P0 | Belum | – | 0.5 | 0 |  |  | Aktivitas manusia
WP-G3 | P5 Review & User Proxy | W5 | Semua | Gate G3: MVP Definition of Done (PRD §13.1) | Happy path E2E, semua AC P0 lulus di CI & staging, tanpa temuan kritis, dokumentasi operator lengkap | PO | – | WP-E2E-01..03, WP-SEC-01, WP-4.3, WP-7.1, WP-6.8, WP-G5 | – | AC-01–AC-20 | P0 | Belum | – | 1 | 0 |  |  | Aktivitas manusia; setelah staging
WP-6.2 | P6 Product completeness | W5 | M12 | E2E Browser QA agent (C19) | Playwright di sandbox node, screenshot sebagai evidence User Proxy | AG-07, AG-08 | AG-13 | WP-INT-06 | FR-088–090 | AC-11 | P1 | Belum | – | 1.5 | 0.6
WP-6.3 | P6 Product completeness | W5 | M18, Infra | Preview subdomain (ADR-008) | Container preview terisolasi + routing Caddy preview-*.domain | AG-06, AG-08 | AG-13 | WP-INT-06 | FR-138 | – | P1 | Belum | – | 1 | 0.4
WP-6.4 | P6 Product completeness | W5 | M16, M19 | Knowledge FR-127 & dashboard observability | Cari riwayat percakapan/task; Prometheus/Grafana opsional | AG-09, AG-06 | AG-00 | WP-INT-06 | FR-127, FR-150 | AC-16 | P1 | Belum | – | 1 | 0.4
WP-6.5 | P6 Product completeness | W5 | M10 | Egress proxy untuk install dependency 🔒 | Profil deps_install via allowlist (ADR-007) | AG-03, AG-06 | AG-13 | WP-4.3 | FR-073 | AC-07 | P1 | Belum | – | 0.8 | 0.3
WP-6.6 | P6 Product completeness | W5 | Semua | Review biaya & usability pilot | Ukur metrik §1.3 (task success, evidence, traceability, approval, biaya) pada task representatif | PO | – | WP-INT-07, WP-E2E-01 | – | – | P1 | Belum | – | 4 | 0 |  |  | Aktivitas manusia + pilot user
WP-6.7 | P6 Product completeness | W5 | Frontend | Audit aksesibilitas & UX (NFR-09, NFR-12) | Keyboard nav, label, kontras, state empty/loading/error, lokalisasi; perbaikan temuan | AG-10, AG-11 | AG-12 | WP-INT-04 | FR-026–040 | – | P1 | Belum | – | 1 | 0.4
WP-6.8 | P6 Product completeness | W4 | Infra | Dokumentasi operator final (PRD §13.1) | Install, update, backup, restore, konfigurasi provider, troubleshooting — diuji pada clean install | AG-06 | OPS | WP-INT-06 | FR-149 | AC-20 | P0 | Belum | RUNBOOK draft ada (WP-1.5) | 0.6 | 0.2
WP-6.9 | P6 Product completeness | W5 | M30 | Monitoring biaya & token realtime (stream, rollup, halaman, alert) | Event usage.event per panggilan (Redis + SSE), rollup per menit, halaman /usage/live, breakdown, alert budget 50/80/100%, label aktual/estimasi/resmi/tidak tersedia; migrasi 0009 schema-first (K21 OI-38) | AG-07, AG-11 | AG-13 | WP-6.4 | FR-283–287, FR-290–291 | AX-19 | P0 | Belum | – | 2 | 0.8 |  |  | Prototipe UI di WP-DEMO-04; ADR-067 diputuskan di sini
WP-6.10 | P6 Product completeness | W5 | M30 | Rekonsiliasi Usage & Cost Admin API (opsional) 🔒 | Container worker-integrations antrean integrations (K21 OI-40), polling ≥ 60 dtk, filter api_key_ids/workspace_ids (OI-51), selisih per model per menit/hari; kunci admin tidak pernah keluar dari worker-integrations | AG-07, AG-18 | AG-13 🔒 | WP-6.9 | FR-288–289, FR-292 | AX-20 | P1 | Belum | – | 1 | 0.4 |  |  | Butuh akun organisasi + Admin API key; akun individual → hanya estimasi
WP-G6 | P6 Product completeness | W5 | Semua | Gate G6: exit Product completeness | Semua P0 + P1 yang disepakati lulus; review biaya & usability pilot; monitoring biaya & token (AX-19, AX-20 bila kredensial ada) | PO | – | WP-6.2..6.10 | – | AX-19, AX-20 | P1 | Belum | – | 0.5 | 0 |  |  | Aktivitas manusia
WP-7.1 | P7 Staging delivery | W5 | Infra | Staging VPS KodeKantor | Ubuntu LTS, TLS, firewall, gVisor, backup & restore drill, smoke, rollback rehearsal | AG-14 + OPS | PO (G7) | WP-E2E-03, WP-4.3 | FR-136–143, FR-149 | AC-20 | P0 | Belum | – | 2 | 0.5
WP-7.2 | P7 Staging delivery | W5 | M18 | Fitur deployment staging (M18) | Preflight, staging, smoke, rollback; production tetap gated | AG-08, AG-14 | AG-13 | WP-7.1 | FR-136–143 | AC-13, AC-20 | P2 | Sebagian | preflight + staging build/smoke di snapshot | 1 | 0.4
WP-DEMO-01 | Demo | W3 | Semua (IDE) | Live demo replay dari eksekusi nyata | Rekam 3 skenario (calc, calc-debug, calc-gap) di stack nyata, lalu halaman replay interaktif bergaya KodeKantor | AG-17 | AG-00 | WP-INT-03 | – | AC-04–AC-13, AC-18 | P1 | Selesai | Artifact KodeKantor Replay; uji Playwright 596/596 lulus (desktop/ponsel, terang/gelap) | 1 | 0.41 | 0.409 | 44.7
WP-0.12 | P0 Discovery & contracts | W3 | Perluasan | Rancangan perluasan platform | PLATFORM_EXPANSION.md + KONTRAK v2 (§9b), ADR-036..056, konfigurasi, ancaman T11–T18, kriteria AX-01..AX-11 | AG-00 | AG-13; PO | WP-0.8 | – (di luar PRD v1.0) | AX-01–AX-11 | P1 | Sebagian | docs/PLATFORM_EXPANSION.md | 0.6 | 0.1 |  |  | ADR Proposed menunggu PO
WP-DEMO-02 | Demo | W3 | Perluasan | Prototipe modul perluasan di live demo | Portal AI, koneksi GitHub App, Portfolio — klik-able, berlabel prototipe & data contoh | AG-17 | AG-00 | WP-0.12, WP-DEMO-01 | – | – | P2 | Selesai | Artifact KodeKantor Replay versi 2; uji Playwright 896/896 lulus | 0.8 | 0.4 |  |  | Token sesi lanjutan tidak dilaporkan
WP-0.13 | P0 Discovery & contracts | W3 | Perluasan | Paket dokumen v2: agent, SRS, desain implementasi, PRD v2.0 | registry.v2.yaml (53 entri) + validator v1/v2, SYSTEM_SPEC.md, FR-160..220, IMPLEMENTATION_DESIGN_V2.md, API/DATA_MODEL v2, PRD v2.0 (Word/PDF) dengan tech stack & mockup | AG-00 | AG-13; PO | WP-0.12 | FR-160–220 | AX-01–AX-11 | P1 | Sebagian | docs/SYSTEM_SPEC.md, docs/IMPLEMENTATION_DESIGN_V2.md, docs/PRD_v2.md, agents/registry.v2.yaml | 0.8 | 0.3 |  |  | Rancangan; menunggu persetujuan PO
WP-0.14 | P0 Discovery & contracts | W3 | Perluasan v2.1 | Paket dokumen v2.1: SDLC end-to-end, Developer Workspace v2, tier S/M/L | SDLC_SCALE_DESIGN.md (KONTRAK v2.1), FR-221..258, UC-21..24, NFR-23..27, AX-12..18, ADR-057..062, desain §13, API §13, DATA_MODEL V2.9–V2.10, PRD v2.1 | AG-00 | AG-13; PO | WP-0.13 | FR-221–258 | AX-12–AX-18 | P1 | Sebagian | docs/SDLC_SCALE_DESIGN.md, docs/PRD_v2.1.md | 0.8 | 0.3 |  |  | Rancangan; menunggu persetujuan PO
WP-DEMO-03 | Demo | W3 | Perluasan v2.1 | Editor kode interaktif, test nyata via Pyodide, papan SDLC, skala S/M/L di live demo | Edit file project hasil rekaman (diff, simpan, konflik 3-way), jalankan test hasil editan di browser (Pyodide) dengan fallback rekaman, papan SDLC 8 fase dari bukti nyata, halaman tier berlabel rancangan | AG-17 | AG-00 | WP-DEMO-02, WP-0.14 | FR-235–240 (prototipe) | – | P1 | Selesai | Artifact KodeKantor Replay versi 3; uji Playwright 1356/1356 lulus; Pyodide: 11/11 test cocok rekaman run b8a1fe83 | 1.5 | 0.9 |  |  | Pyodide = WebAssembly di browser, bukan sandbox KodeKantor
WP-0.15 | P0 Discovery & contracts | W3 | Perluasan v2.2 | Paket dokumen v2.2: polyglot language packs, lingkungan integrasi, monitoring biaya & token | POLYGLOT_INTEGRATION_DESIGN.md (KONTRAK v2.2 K14–K21), FR-259..292, UC-25..27, NFR-28..31, AX-19..24, ADR-063..068, T24–T28, desain §14, API §14, DATA_MODEL V2.11–V2.12, PRD v2.2 | AG-00 | AG-13; PO | WP-0.14 | FR-259–292 | AX-19–AX-24 | P1 | Sebagian | docs/POLYGLOT_INTEGRATION_DESIGN.md, docs/PRD_v2.2.md | 0.8 | 0.3 |  |  | Rancangan; menunggu persetujuan PO
WP-DEMO-04 | Demo | W3 | Perluasan v2.2 | Halaman monitoring biaya & token + language packs & integrasi di live demo | Replay 61 event usage dari rekaman nyata (scripted provider, biaya tidak tersedia), simulasi tarif dari input user, alert budget, halaman language pack & lingkungan integrasi berlabel rancangan | AG-17 | AG-00 | WP-DEMO-03, WP-0.15 | FR-283–287, FR-290 (prototipe) | – | P1 | Selesai | Artifact KodeKantor Replay versi 5; uji Playwright 1662/1662 lulus | 1 | 0.6 |  |  | Biaya resmi & rekonsiliasi tidak tersedia di demo (tanpa Admin API)
WP-9.0 | P9 GitHub | W7 | M24, M22 | Kunci kontrak v2 sebelum W7 | Loader registry schema 2 (registry.v2.yaml → registry.yaml), RunScope, ApprovalGrant, approvals scope v2, migrasi 0002–0003 schema-first di balik flag; ADR-050..056 Accepted | AG-00 | AG-13 🔒; PO | WP-G3, WP-0.13 | FR-213, FR-216 | AX-11 | P0 | Belum | – | 1 | 0.4 |  |  | Prasyarat semua WP P9–P12
WP-9.1 | P9 GitHub | W7 | M22 | Registrasi GitHub App & secret | App dengan permission minimum (tanpa Workflows), private key sebagai secret file, webhook secret, URL callback | OPS + AG-18 | AG-13 🔒 | WP-9.0, WP-0.9 | FR-185–186, FR-195 | AX-01 | P0 | Belum | – | 0.5 | 0.1 |  |  | Butuh akun GitHub PO
WP-9.2 | P9 GitHub | W7 | M22 | Instalasi, callback, webhook HMAC | Tabel github_*, state nonce, verifikasi X-Hub-Signature-256, dedupe delivery | AG-18 | AG-13 🔒 | WP-9.1 | FR-185, FR-187, FR-194 | AX-03 | P0 | Belum | – | 1.5 | 0.6
WP-9.3 | P9 GitHub | W7 | M22, M03 | Import & pull repo privat | Token per operasi (1 repo, contents:read), clone tanpa token di URL/config, deteksi stack & index | AG-18, AG-09 | AG-13 🔒 | WP-9.2 | FR-188–190 | AX-01 | P0 | Belum | – | 1.5 | 0.6
WP-9.4 | P9 GitHub | W7 | M22, M15 | Push branch & buka PR via R3 | Approval terikat repo+branch+head_commit, secret scan pre-push, blokir .github/workflows, tanpa force push | AG-18, AG-08 | AG-13 🔒 | WP-9.3 | FR-191–193, FR-196 | AX-02 | P0 | Belum | – | 2 | 0.8
WP-9.5 | P9 GitHub | W7 | M22 | UI integrasi GitHub | Settings → Hubungkan GitHub, pilih repo, import, status PR di task | AG-10, AG-11 | AG-12 | WP-9.3 | FR-185, FR-187, FR-196 | AX-01, AX-02 | P0 | Belum | – | 1.5 | 0.6
WP-G9 | P9 GitHub | W7 | M22 | Gate G9: GitHub end-to-end | Repo privat: import → task → approval → PR terbuka; sign-off keamanan | PO | – | WP-9.4, WP-9.5 | – | AX-01–AX-03 | P0 | Belum | – | 0.5 | 0 |  |  | Aktivitas manusia
WP-10.1 | P10 Portal AI | W8 | M24 | Capability registry & provider gateway | capabilities.yaml, providers.yaml, ImageProvider/DocumentEngine interface, usage per capability, kill switch; server tool lewat ToolGateway (ADR-051) | AG-07 | AG-00 | WP-9.0, WP-G9 | FR-163, FR-165, FR-213–220 | AX-04–AX-07, AX-11 | P0 | Belum | – | 1.5 | 0.6
WP-10.2 | P10 Portal AI | W8 | M21 | Assistant backend: ruang, thread, streaming | spaces/threads/messages, SSE, regenerate, label sensitivitas | AG-19 | AG-00 | WP-10.1 | FR-160–163, FR-165 | – | P0 | Belum | – | 2 | 0.8
WP-10.3 | P10 Portal AI | W8 | M21 | Riset web bersitasi | web_search/web_fetch, mode cepat/mendalam, sitasi tersimpan & tampil, allow/block domain, anggaran pencarian | AG-19 | AG-13 | WP-10.2 | FR-164, FR-166–170 | AX-04 | P0 | Belum | – | 2 | 0.8
WP-10.4 | P10 Portal AI | W8 | M21 | Engine dokumen ganda + asset store | Agent Skills pptx/docx/xlsx/pdf + engine lokal sandbox, signed URL unduhan | AG-19, AG-03 | AG-13 | WP-10.2 | FR-171–174 | AX-05, AX-06 | P0 | Belum | – | 2 | 0.8
WP-10.5 | P10 Portal AI | W8 | M21 | Frontend Portal AI | Chat, panel sitasi, pembuat dokumen, kuota capability | AG-20 | AG-12 | WP-10.3, WP-10.4 | FR-161–162, FR-164, FR-167–168, FR-171 | AX-04, AX-05 | P0 | Belum | – | 2 | 0.8
WP-10.6 | P10 Portal AI | W8 | M21 | Evaluasi akurasi sitasi & biaya | Set pertanyaan uji berjawaban terverifikasi; ukur sitasi tepat, jawaban tanpa sumber, biaya per jawaban | AG-12 | PO | WP-10.5 | – | AX-04 | P0 | Belum | – | 1.5 | 0.5
WP-10.7 | P10 Portal AI | W8 | M30, M24 | Biaya capability (web search, gambar, code execution) ke monitoring | usage_events.capability_usage_id + CHECK tepat satu (K21 OI-43), entri tarif server tool & vendor di PRICING_PATH | AG-07, AG-19 | AG-00 | WP-10.1, WP-6.9 | FR-283, FR-286 | AX-19 | P1 | Belum | – | 0.8 | 0.3
WP-G10 | P10 Portal AI | W8 | M21 | Gate G10: Portal AI inti | Evaluasi lulus ambang yang disetujui PO; data-flow per capability terdokumentasi | PO | – | WP-10.6, WP-10.7 | FR-219 | AX-04–AX-06, AX-11 | P0 | Belum | – | 0.5 | 0 |  |  | Aktivitas manusia
WP-11.1 | P11 Gambar & analisis | W9 | M21 | ADR-040a: pilih vendor gambar | Uji kualitas teks dalam gambar, edit, biaya, kebijakan data vendor | PO + AG-00 | – | WP-G10 | FR-181 | AX-07 | P1 | Belum | – | 1 | 0.2
WP-11.2 | P11 Gambar & analisis | W9 | M21 | ImageProvider + moderasi + provenance + kuota 🔒 | Adapter vendor terpilih, contract test, moderasi prompt, galeri | AG-19 | AG-13 | WP-11.1 | FR-181–183, FR-215 | AX-07 | P1 | Belum | – | 2 | 0.8
WP-11.3 | P11 Gambar & analisis | W9 | M21 | Upload file & tanya jawab dokumen (tanpa embedding, ADR-046) | Ekstraksi di sandbox, chunk + ringkasan kontekstual Claude + FTS/pg_trgm, jawaban via blok search_result bersitasi; eval Recall@8 ≥ 0.85 | AG-19 | AG-00 | WP-G10 | FR-175–177 | AX-10 | P1 | Belum | – | 2 | 0.8
WP-11.4 | P11 Gambar & analisis | W9 | M21 | Analisis data | CSV/XLSX → kode di sandbox/code execution → tabel/grafik + kode dapat diperiksa | AG-19, AG-03 | AG-13 | WP-G10 | FR-179–180 | – | P1 | Belum | – | 1.5 | 0.6
WP-11.5 | P11 Gambar & analisis | W9 | M21 | Frontend gambar, KB, analisis | Galeri, upload, hasil analisis | AG-20 | AG-12 | WP-11.2, WP-11.3, WP-11.4 | FR-180, FR-183 | AX-07 | P1 | Belum | – | 1.5 | 0.6
WP-G11 | P11 Gambar & analisis | W9 | M21 | Gate G11 | Moderasi & kuota teruji; biaya per gambar terukur | PO | – | WP-11.5 | – | AX-07, AX-10 | P1 | Belum | – | 0.5 | 0 |  |  | Aktivitas manusia
WP-12.1 | P12 Portfolio | W10 | M23 | Model konten & API portfolio | profil, item, versi, publikasi; visibility draft/public | AG-21 | AG-00 | WP-G10 | FR-197–199, FR-202–205, FR-212 | AX-09 | P1 | Belum | – | 1.5 | 0.6
WP-12.2 | P12 Portfolio | W10 | M23 | Impor proyek dari GitHub & KodeKantor | README, bahasa, topik; repo privat hanya metadata terpilih | AG-21, AG-18 | AG-13 | WP-12.1, WP-G9 | FR-200–201 | AX-08 | P1 | Belum | – | 1 | 0.4
WP-12.3 | P12 Portfolio | W10 | M23 | CV DOCX/PDF & asisten lamaran | Template ATS sans-serif; web_fetch lowongan → saran (draft); tanpa mengarang pencapaian | AG-21, AG-19 | AG-12 | WP-12.1, WP-10.4 | FR-203–204, FR-206–207 | AX-05, AX-09 | P1 | Belum | – | 1.5 | 0.6
WP-12.4 | P12 Portfolio | W10 | M23 | Situs publik + publish R3 🔒 | Statis di portfolio.<domain> atau GitHub Pages; pratinjau, cek privasi, approval | AG-21, AG-06 | AG-13 | WP-12.1 | FR-205, FR-208–210 | AX-08 | P1 | Belum | – | 1.5 | 0.6
WP-12.5 | P12 Portfolio | W10 | M23 | Frontend Portal Portfolio | Editor profil/item, CV, pratinjau situs | AG-21 | AG-12 | WP-12.2..12.4 | FR-197, FR-199 | AX-08, AX-09 | P1 | Belum | – | 1.5 | 0.6
WP-G12 | P12 Portfolio | W10 | M23 | Gate G12 | CV & situs publik dari data nyata pengguna, disetujui PO | PO | – | WP-12.5 | – | AX-08, AX-09 | P1 | Belum | – | 0.5 | 0 |  |  | Aktivitas manusia
WP-13.0 | P13 SDLC & tier M | W11 | M25–M27 | Kunci kontrak v2.1 (ADR-057..062 Accepted, migrasi 0007–0008 schema-first, registry phase P13/P14) | Transisi take-over di states.py, validator registry menerima P13/P14, tabel tier L inert | AG-00 | AG-13; PO | WP-G3, WP-0.14 | FR-221, FR-245 | – | P1 | Belum | – | 1 | 0.4
WP-13.1 | P13 SDLC & tier M | W11 | M26 | Developer workspace v2: operasi file, take-over, konflik 3-way, Git manual | create/rename/delete + version check, take-over interrupted/user_takeover, bukti stale, diff 3-way, stage/commit/branch user | AG-09, AG-10, AG-02 | AG-13 | WP-13.0 | FR-235–237, FR-244 | AX-12 | P0 | Belum | – | 2 | 0.8
WP-13.2 | P13 SDLC & tier M | W11 | M26 | Run & test dari IDE + preview, format/lint on save | Profil run.*, test terpilih (initiated_by=user), preview ADR-008, formatter sebagai patch | AG-03, AG-10 | AG-08 | WP-13.0 | FR-238–240 | AX-13 | P1 | Belum | – | 1.5 | 0.6
WP-13.3 | P13 SDLC & tier M | W11 | M26 | Terminal interaktif sandbox untuk user 🔒 | PTY di sandbox, WebSocket tiket sekali pakai, network off, limit & idle timeout, audit teredaksi, default nonaktif (ADR-059) | AG-03, AG-10 | AG-13 🔒 | WP-13.2 | FR-241 | AX-13 | P1 | Belum | – | 1.5 | 0.6 |  |  | Ancaman T19
WP-13.4 | P13 SDLC & tier M | W11 | M25 | Work item Program/Epic/Story, dekomposisi A03, papan SDLC | work_items, ProgramPlan disetujui user, DAG & penjadwalan paralel, roll-up status deterministik | AG-08, AG-10 | AG-00 | WP-13.0 | FR-221–224, FR-226–227 | AX-14, AX-15 | P1 | Belum | – | 2 | 0.8
WP-13.5 | P13 SDLC & tier M | W11 | M25 | Merge queue lokal (rebase + profil test wajib) | Serialisasi apply per repo; gagal → needs_changes; branch target terlindungi | AG-08 | AG-13 | WP-13.4 | FR-225 | AX-14 | P0 | Belum | – | 1.5 | 0.6
WP-13.6 | P13 SDLC & tier M | W11 | M25 | Traceability export + dashboard program | requirement → story → task → commit → test → acceptance → release; CSV/JSON/PDF | AG-09, AG-11 | AG-08 | WP-13.4 | FR-231–232 | AX-15 | P0 | Belum | – | 1 | 0.4
WP-13.7 | P13 SDLC & tier M | W11 | M27 | Pool executor tier M + failover + workspace multi-node 🔒 | Registrasi node & token rotasi, lease, failover dari checkpoint, git bundle/volume bersama, budget program, kapasitas transparan | AG-06, AG-03, AG-01 | AG-13 🔒 | WP-13.0 | FR-245–248, FR-255, FR-258 | AX-16 | P1 | Belum | – | 2.5 | 1 |  |  | Ancaman T21
WP-13.8 | P13 SDLC & tier M | W11 | M27 | SSO OIDC 🔒 | Pemetaan grup → role, login lokal dapat dimatikan, pertukaran code di worker-integrations | AG-01, AG-11 | AG-13 🔒 | WP-13.0 | FR-250 | AX-17 | P1 | Belum | – | 1 | 0.4 |  |  | Bagian OIDC AX-17 diverifikasi di G13
WP-13.9 | P13 SDLC & tier M | W11 | M27 | Repo besar & multi-repo | Sparse checkout per task, index simbol inkremental di sandbox, batas konteks A04, story lintas repo | AG-02, AG-07 | AG-00 | WP-13.0 | FR-253–254 | AX-14, AX-18 | P1 | Belum | – | 2 | 0.8
WP-13.10 | P13 SDLC & tier M | W11 | M25 | Release train + environment registry + CODEOWNERS + insiden → story | Changelog dari task/commit, promosi dev→staging, production tetap R3 | AG-08, AG-14 | AG-00 | WP-13.5 | FR-228–229, FR-233–234 | AX-15 | P2 | Belum | – | 1.5 | 0.6
WP-13.11 | P13 SDLC & tier M | W11 | M25 | Aktivasi agent SDLC tier M (A05, A06, B12, C18, C19, E28, F30, F32) per G8 | Contract test + eval set per agent; tetap 53 entri registry | AG-15 | PO | WP-13.4 | FR-227 | – | P1 | Belum | – | 1.5 | 0.5
WP-13.12 | P13 SDLC & tier M | W11 | M25 | Status CI GitHub sebagai syarat merge queue | ci.get_checks via GitHub App; sah hanya untuk head_commit ter-push yang tidak berubah oleh rebase; CI pasca-merge gagal → story perbaikan | AG-18, AG-08 | AG-13 | WP-13.5, WP-G9 | FR-230 | AX-14 | P1 | Belum | – | 1 | 0.4
WP-G13 | P13 SDLC & tier M | W11 | M25–M27 | Gate G13: SDLC end-to-end tier M | Program kecil (≥1 epic, ≥3 story) end-to-end di tier M dengan merge queue & traceability; edit/take-over/run/test/terminal dari IDE; failover node; login OIDC | PO + AG-13 | – | WP-13.1..13.12 | – | AX-12–AX-16, AX-17 (OIDC) | P1 | Belum | – | 0.5 | 0 |  |  | Aktivitas manusia
WP-14.0 | P14 Enterprise tier L | W12 | M27 | ADR orkestrator tier L (VM pool vs Kubernetes) dari data beban tier M | Termasuk keputusan akses DB node (OI-32) | AG-00 + PO | AG-13 | WP-G13 | FR-246 | – | P2 | Belum | – | 0.5 | 0.2 |  |  | Keputusan PO
WP-14.1 | P14 Enterprise tier L | W12 | M27 | Organisasi/tenant 🔒 | Scope organisasi di query, path, cache, budget, audit; 404 lintas org | AG-01, AG-09 | AG-13 🔒 | WP-14.0 | FR-252 | AX-17 | P2 | Belum | – | 2 | 0.8 |  |  | Ancaman T20
WP-14.2 | P14 Enterprise tier L | W12 | M27 | SAML + SCIM 🔒 | Deprovision mencabut sesi ≤ 5 menit [Menebak]; JIT nonaktif default | AG-01 | AG-13 🔒 | WP-14.1 | FR-250–251 | AX-17 | P2 | Belum | – | 1.5 | 0.6 |  |  | Ancaman T22
WP-14.3 | P14 Enterprise tier L | W12 | M27 | Driver sandbox microVM 🔒 | Firecracker/Kata, profil sandbox sama | AG-03 | AG-13 🔒 | WP-14.0 | FR-249 | AX-17 | P2 | Belum | – | 2 | 0.8
WP-14.4 | P14 Enterprise tier L | W12 | M27 | HA & DR | PostgreSQL replika/failover, Redis HA, backup terenkripsi, DR drill RPO/RTO | AG-06 + OPS | AG-13 | WP-14.0 | FR-256 | AX-17 | P2 | Belum | – | 1.5 | 0.4
WP-14.5 | P14 Enterprise tier L | W12 | M27 | SIEM export + governance biaya organisasi | Rantai hash audit, OTLP/syslog, anggaran per org | AG-01, AG-11 | AG-13 | WP-14.1 | FR-255, FR-257 | AX-17 | P2 | Belum | – | 1 | 0.4
WP-14.6 | P14 Enterprise tier L | W12 | M26 | Language server + debugger di sandbox | LSP & DAP per stack; kanal diputuskan (OI-25); backlog LSP/DAP pack L1 v2.2 (OI-50) | AG-03, AG-10 | AG-13 | WP-G13 | FR-242–243 | – | P2 | Belum | – | 2 | 0.8
WP-14.7 | P14 Enterprise tier L | W12 | M27 | Benchmark repo besar & beban | Repo ≥ 1 juta LOC [Menebak]; kapasitas tier L | AG-12 | PO | WP-13.9, WP-14.0 | FR-253 | AX-18 | P2 | Belum | – | 1 | 0.3
WP-14.8 | P14 Enterprise tier L | W12 | M25 | Aktivasi agent tier L (B08, B15, D25, D26, F31, F33, F34, G36, H38–H40) per G8 | Contract test + eval set per agent; D24 → WP-15.10, B11 → WP-16.6 (v2.2) | AG-15 | PO | WP-G13 | FR-234 | – | P2 | Belum | – | 2 | 0.7
WP-G14 | P14 Enterprise tier L | W12 | M27 | Gate G14: Enterprise tier L | SAML/SCIM, isolasi tenant, microVM, DR drill, SIEM, benchmark repo besar; sign-off keamanan | PO + AG-13 | – | WP-14.1..14.8 | – | AX-17, AX-18 | P2 | Belum | – | 0.5 | 0 |  |  | Aktivitas manusia
WP-15.0 | P15 Polyglot language packs | W13 | M28 | Framework language pack: registry, pipeline image, proxy dependensi, deteksi polyglot (H41) 🔒 | ADR-063/064 Accepted, registry pack berversi, pipeline image (pin digest, SBOM, scan), dep-proxy per ekosistem, deteksi monorepo, validator registry menerima P15/P16 (OI-46), kontrak tool deps.audit (OI-47), produk proxy diputuskan (OI-49) | AG-03, AG-06 | AG-13 🔒 | WP-6.5, WP-13.0 | FR-259–260, FR-263–264, FR-267 | AX-21 | P0 | Belum | – | 2.5 | 1 |  |  | Ancaman T24, T27
WP-15.1 | P15 Polyglot language packs | W13 | M28 | Pack JVM (Java/Kotlin, Spring Boot) | L1: template, deps via proxy, build, test (JUnit/setara), lint, format, run, package | AG-03 | AG-08 | WP-15.0 | FR-261–262 | AX-21 | P1 | Belum | – | 1.5 | 0.6
WP-15.2 | P15 Polyglot language packs | W13 | M28 | Pack .NET (C#, ASP.NET Core) | L1: template, deps via proxy, build, test (JUnit/setara), lint, format, run, package | AG-03 | AG-08 | WP-15.0 | FR-261–262 | AX-21 | P1 | Belum | – | 1.5 | 0.6
WP-15.3 | P15 Polyglot language packs | W13 | M28 | Pack Go | L1: template, deps via proxy, build, test (JUnit/setara), lint, format, run, package | AG-03 | AG-08 | WP-15.0 | FR-261–262 | AX-21 | P1 | Belum | – | 1 | 0.4
WP-15.4 | P15 Polyglot language packs | W13 | M28 | Pack PHP/Laravel | L1: template, deps via proxy, build, test (JUnit/setara), lint, format, run, package | AG-03 | AG-08 | WP-15.0 | FR-261–262 | AX-21 | P1 | Belum | – | 1 | 0.4
WP-15.5 | P15 Polyglot language packs | W13 | M28 | Pack Ruby (L2) | L2: deps via proxy, build, test, lint | AG-03 | AG-08 | WP-15.0 | FR-262 | AX-21 | P1 | Belum | – | 0.8 | 0.3
WP-15.6 | P15 Polyglot language packs | W13 | M28 | Pack C++ (L2) | L2: CMake + vcpkg/Conan via proxy, build, test (CTest/GoogleTest), lint; kuota CPU/RAM khusus (T27) | AG-03 | AG-08 | WP-15.0 | FR-262 | AX-21 | P1 | Belum | – | 1 | 0.4
WP-15.7 | P15 Polyglot language packs | W13 | M28 | Perluasan pack Node/JS/TS/React + Python | Profil seragam pack, template React/Node/FastAPI, laporan test seragam | AG-03, AG-10 | AG-08 | WP-15.0 | FR-261–262 | AX-21 | P1 | Belum | – | 1 | 0.4
WP-15.8 | P15 Polyglot language packs | W13 | M28 | Pack mobile: Flutter (web + Android) & React Native (Android), penanda target non-Linux | Build Android & web di sandbox; iOS/macOS/Windows/emulator → CI eksternal sebagai bukti (ADR-068) | AG-03, AG-06 | AG-13 | WP-15.0 | FR-268, FR-270 | AX-21 | P2 | Belum | – | 2 | 0.8 |  |  | Image besar (RP-01)
WP-15.9 | P15 Polyglot language packs | W13 | M28 | Pack SQL (migrasi, lint, test terhadap DB ephemeral) | Flyway/Liquibase, lint SQL, test terhadap PostgreSQL/MySQL/SQL Server dev ephemeral | AG-03, AG-09 | AG-08 | WP-15.0 | FR-269 | AX-21 | P1 | Belum | – | 1.2 | 0.5
WP-15.10 | P15 Polyglot language packs | W13 | M28 | Set evaluasi agent per bahasa + petunjuk pack + aktivasi D24 | Eval implementasi + bug seeded per pack L1 (ambang default ≥ 70%, OI-48), petunjuk B14/C17/C20, deps.audit, aktivasi D24 per G8 | AG-12, AG-15 | PO | WP-15.1..15.9 | FR-265–266 | AX-22 | P1 | Belum | – | 2 | 1.5 |  |  | Token eval dihitung terpisah per bahasa
WP-G15 | P15 Polyglot language packs | W13 | M28 | Gate G15: polyglot language packs gelombang 1 | Matriks test per pack di CI hijau; eval per pack L1 lulus ambang PO; sign-off keamanan proxy dependensi | PO + AG-13 | – | WP-15.0..15.10 | – | AX-21, AX-22 | P1 | Belum | – | 0.5 | 0 |  |  | Aktivitas manusia
WP-16.0 | P16 Integrasi multi-service | W14 | M29 | ADR & desain keamanan lingkungan integrasi 🔒 | ADR-065/066 Accepted; NETWORKS=1 hanya di socket proxy node executor (OI-41); syarat tier S (OI-39) & pemutus pengecualian (OI-45) diputuskan PO | AG-00, AG-13 | PO | WP-G15, WP-13.7 | FR-275 | – | P1 | Belum | – | 0.8 | 0.3 |  |  | Ancaman T25, T28
WP-16.1 | P16 Integrasi multi-service | W14 | M29 | Env runner: spec, validator policy, network per env, kuota, TTL 🔒 | Spec deklaratif tervalidasi (image terdaftar, tanpa privileged/host mount/host network/egress, secret scan), network internal per env, kuota, sweeper TTL | AG-03 | AG-13 🔒 | WP-16.0 | FR-275, FR-277–278, FR-280 | AX-23 | P1 | Belum | – | 2.5 | 1 |  |  | Ancaman T25, T28
WP-16.2 | P16 Integrasi multi-service | W14 | M29 | Katalog service & kontrak (validasi, diff breaking, mock) | OpenAPI/AsyncAPI/Protobuf/GraphQL di repo, validasi, diff breaking, mock dari kontrak | AG-09, AG-08 | AG-00 | WP-16.0 | FR-271–274, FR-276 | AX-24 | P1 | Belum | – | 2 | 0.8
WP-16.3 | P16 Integrasi multi-service | W14 | M29 | Contract test & E2E lintas service + syarat merge queue | suite = integration, log per service & trace sebagai bukti; entri merge queue gagal CONTRACT_BREAKING | AG-08, AG-12 | AG-13 | WP-16.1, WP-16.2 | FR-279, FR-282 | AX-23, AX-24 | P1 | Belum | – | 2 | 0.8
WP-16.4 | P16 Integrasi multi-service | W14 | M29 | Seed data, migrasi DB di env (B12, H38, H39) | Data sintetis, secret palsu yang dibangkitkan, migrasi pack SQL di env | AG-09 | AG-08 | WP-16.1, WP-15.9 | FR-269, FR-278 | AX-23 | P1 | Belum | – | 1.2 | 0.5 |  |  | H38/H39 baru aktif di P14; sebelum itu B12 + manusia (K21)
WP-16.5 | P16 Integrasi multi-service | W14 | M29 | UI peta service & lingkungan | Peta service, kesehatan, log, hasil test per env; prototipe di WP-DEMO-04 | AG-10 | AG-08 | WP-16.1 | FR-281 | – | P1 | Belum | – | 1.2 | 0.5
WP-16.6 | P16 Integrasi multi-service | W14 | M29 | Aktivasi B11 + contract test C18 lintas service per G8 | Contract test + eval set B11; C18 diperluas ke lintas service | AG-15 | PO | WP-16.3 | FR-272–274 | – | P1 | Belum | – | 1 | 0.5
WP-G16 | P16 Integrasi multi-service | W14 | M29 | Gate G16: sistem enterprise terintegrasi multi-bahasa | ≥ 3 service beda bahasa + DB + broker naik terisolasi, E2E lintas service lulus, breaking change memblokir merge queue; sign-off keamanan | PO + AG-13 | – | WP-16.0..16.6 | – | AX-23, AX-24 | P1 | Belum | – | 0.5 | 0 |  |  | Aktivitas manusia
WP-8.1 | P8 Specialist rollout | W6 | M12, M15 | Wave A specialist | D24 Dependency & supply chain, C18 Integration & API testing (C19 sudah di WP-6.2) | AG-15 | AG-00, PO (G8) | WP-6.2, WP-G3 | FR-041–047 | AC-06 | P1 | Belum | – | 1.5 | 0.7 |  |  | Aktifkan hanya bila manfaat terukur (R-06)
WP-8.2 | P8 Specialist rollout | W6 | M08 | Wave B specialist | A06 Change impact & risk, A05 Software architect | AG-15 | AG-00, PO (G8) | WP-8.1 | FR-041–047 | – | P1 | Belum | – | 1.5 | 0.7
WP-8.3 | P8 Specialist rollout | W6 | M18 | Wave C specialist (dukungan staging) | F30 Build & CI, F31 Infrastructure as Code, F32 Deployment & Release | AG-15 | AG-00, PO (G8) | WP-8.2, WP-7.1 | FR-136–143 | AC-20 | P2 | Belum | – | 2 | 1
WP-8.4 | P8 Specialist rollout | W6 | Beragam | Wave D specialist (P2, atas permintaan pilot) | B08, B11, B12, B15, D25, D26, E28, E29, F33, F34, G36, H38, H39, H40 | AG-15 | AG-00, PO (G8) | WP-8.3 | FR-041–047 | – | P2 | Belum | – | 4 | 2 |  |  | 14 agent; diaktifkan satu per satu
Total | [13 empty] | 166.7 | 62.76 | 6.345 | 636.8
Kolom O–P (biru) = input estimasi yang dapat diubah. Kolom Q–R = aktual terukur. Status dapat dipilih dari daftar.

## Timeline
Timeline
Matriks wave × agent, dihitung otomatis dari sheet WBS (kolom Owner & Wave). ■ = agent memiliki ≥1 WP pada wave tsb.
Agent / peran | Nama | W0 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | Jumlah WP
AG-00 | Lead Architect / Orchestrator | ■ |  | ■ | ■ |  |  |  | ■ |  | ■ |  | ■ | ■ |  | ■ | 17
AG-01 | Backend Core |  | ■ |  | ■ | [7 empty] | ■ | ■ |  |  | 10
AG-02 | Workspace & Git |  | ■ | [9 empty] | ■ |  |  |  | 3
AG-03 | Sandbox & Runtime |  | ■ | ■ | ■ |  | ■ |  |  | ■ | ■ |  | ■ | ■ | ■ | ■ | 22
AG-04 | Frontend Foundation |  | ■ | [13 empty] | 1
AG-05 | Docs & Catalog |  | ■ | [13 empty] | 1
AG-06 | Infra & DevOps |  | ■ |  |  | ■ | ■ |  |  |  |  | ■ | ■ | ■ | ■ |  | 10
AG-07 | Agentic Core |  |  | ■ | ■ |  | ■ |  |  | ■ |  |  | ■ |  |  |  | 9
AG-08 | Workflow & Acceptance |  |  | ■ | ■ |  | ■ |  | ■ |  |  |  | ■ |  |  | ■ | 16
AG-09 | Platform Services |  |  | ■ | ■ |  | ■ |  | ■ |  |  |  | ■ | ■ | ■ | ■ | 10
AG-10 | Frontend Workspace |  |  | ■ | ■ |  | ■ |  | ■ |  |  |  | ■ | ■ | ■ | ■ | 12
AG-11 | Frontend Admin |  |  | ■ | ■ |  | ■ |  | ■ |  |  |  | ■ | ■ |  |  | 8
AG-12 | Integration & E2E QA |  |  |  | ■ | ■ |  |  |  | ■ |  |  |  | ■ | ■ | ■ | 9
AG-13 | Security Reviewer |  |  |  |  | ■ | [6 empty] | ■ | ■ | ■ | ■ | 7
AG-14 | Release & Staging | [5 empty] | ■ | [5 empty] | ■ |  |  |  | 3
AG-15 | Specialist Rollout | [6 empty] | ■ |  |  |  |  | ■ | ■ | ■ | ■ | 8
AG-16 | Design Reviewer (independen) |  |  | ■ | [12 empty] | 1
AG-17 | Demo & Prototype UI |  |  |  | ■ | [11 empty] | 4
AG-18 | Integrations Engineer (GitHub) | [5 empty] | ■ |  | ■ |  |  | ■ | ■ |  |  |  | 7
AG-19 | AI Portal Backend | [8 empty] | ■ | ■ | ■ |  |  |  |  | 8
AG-20 | AI Portal Frontend | [8 empty] | ■ | ■ | [5 empty] | 2
AG-21 | Portfolio Full-stack | [10 empty] | ■ |  |  |  |  | 5
PO | Product Owner (Tira) |  |  |  | ■ | ■ | ■ |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | 16
OPS | Operator VPS |  |  |  | ■ |  | ■ |  | ■ |  |  |  |  | ■ |  |  | 4
Legenda wave
Wave | Fokus |  | Status |  | Agent
W0 | Rancangan & kontrak |  | Selesai |  | AG-00
W1 | Fondasi paralel (6 agent) |  | Selesai (snapshot) |  | AG-01..06
W2 | Layanan domain + UI (5 agent) |  | Selesai (snapshot) |  | AG-07..11
W3 | Integrasi & ADR-021..035 |  | Belum (dihentikan PO) |  | AG-01, 03, 07, 08, 09, 10, 11, 12, PO, OPS
W4 | E2E + gate keamanan + MVP DoD |  | Belum |  | AG-12, AG-13, PO
W5 | Staging VPS + kelengkapan P1 + monitoring biaya & token |  | Belum |  | AG-03, 06, 07, 08, 09, 11, 13, 14, 18, OPS
W6 | Rollout specialist bertahap |  | Belum |  | AG-15, PO
W7 | Kunci kontrak v2 (WP-9.0) + Integrasi GitHub App (P9) |  | Belum |  | AG-00, AG-18, AG-09, AG-08, AG-10, AG-11, OPS, PO
W8 | Portal AI inti (P10) |  | Belum |  | AG-07, AG-19, AG-20, AG-03, AG-12, PO
W9 | Gambar, KB, analisis (P11) |  | Belum |  | AG-19, AG-20, AG-03, PO
W10 | Portal Portfolio (P12) |  | Belum |  | AG-21, AG-18, AG-19, AG-06, PO
W11 | SDLC end-to-end & tier M (P13) |  | Belum |  | AG-00, AG-01, AG-02, AG-03, AG-06, AG-07, AG-08, AG-09, AG-10, AG-11, AG-14, AG-15, AG-18, OPS, PO
W12 | Enterprise tier L (P14) |  | Belum |  | AG-00, AG-01, AG-03, AG-06, AG-09, AG-10, AG-11, AG-12, AG-15, OPS, PO
W13 | Polyglot language packs gelombang 1 (P15) |  | Belum |  | AG-03, AG-06, AG-09, AG-10, AG-12, AG-13, AG-15, OPS, PO
W14 | Lingkungan integrasi multi-service & kontrak (P16) |  | Belum |  | AG-00, AG-03, AG-08, AG-09, AG-10, AG-12, AG-13, AG-15, PO

## RACI
RACI
R = mengerjakan, A = akuntabel/menyetujui, C = dikonsultasi, I = diberi tahu. Satu A per aktivitas.
Aktivitas | AG-00 | AG-01 | AG-02 | AG-03 | AG-04 | AG-05 | AG-06 | AG-07 | AG-08 | AG-09 | AG-10 | AG-11 | AG-12 | AG-13 | AG-14 | AG-15 | AG-17 | AG-18 | AG-19 | AG-20 | AG-21 | PO | OPS | Jumlah A
Kontrak arsitektur & ADR | R |  |  |  |  | C | [7 empty] | C | [7 empty] | A |  | 1
Keputusan ADR Proposed & review FR | R |  |  |  |  | C | [15 empty] | A |  | 1
Backend core & data model | A | R | [5 empty] | I | I | I |  |  |  | C | [9 empty] | 1
Workspace, Git & import aman | A |  | R | [6 empty] | I |  |  |  | C | [9 empty] | 1
Sandbox & isolasi | A |  |  | R |  |  | C | [6 empty] | C | [8 empty] | I | 1
Agentic core (LLM, tools, runtime, approvals) | A | [6 empty] | R | C |  |  |  |  | C | [9 empty] | 1
Workflow, testing, review & User Proxy | A | [6 empty] | C | R |  |  |  |  | C | [7 empty] | I |  | 1
Platform services (projects, IDE, knowledge, admin) | A |  | C | [6 empty] | R | [13 empty] | 1
Frontend foundation & design system | A |  |  |  | R | [5 empty] | I | I | [11 empty] | 1
Frontend IDE & workflow screens | A |  |  |  | C | [5 empty] | R | [10 empty] | C |  | 1
Frontend admin & settings | A |  |  |  | C | [6 empty] | R | [11 empty] | 1
Infra, CI & runbook | A | [5 empty] | R | [6 empty] | C | [8 empty] | C | 1
Katalog, FR & registry agent | A |  |  |  |  | R | [15 empty] | C |  | 1
Integrasi & E2E | A | [6 empty] | C | C | C | C | C | R | [8 empty] | I |  | 1
Sign-off keamanan 🔒 | C |  |  | C |  |  |  | C | [5 empty] | R | [7 empty] | A |  | 1
Readiness gate Claude API | I | [6 empty] | C | [13 empty] | A | R | 1
Staging VPS & drill | [6 empty] | C | [6 empty] | C | R | [6 empty] | A | R | 1
Aktivasi specialist planned | C | [12 empty] | C |  | R | [5 empty] | A |  | 1
Integrasi GitHub App (P9) | A | [12 empty] | C |  |  |  | R |  |  |  | I | C | 1
Portal AI (P10–P11) | A | [12 empty] | C |  |  |  |  | R | R |  | C |  | 1
Keputusan vendor gambar (ADR-040a) | R | [17 empty] | C |  |  | A |  | 1
Portal Portfolio & publikasi (P12) | A | [12 empty] | C | [6 empty] | R | C |  | 1
Live demo & prototipe | A | [15 empty] | R |  |  |  |  | I |  | 1
Monitoring biaya & token realtime (WP-6.9, WP-10.7) | A | [6 empty] | R |  |  |  | R |  | C |  |  |  |  | C |  |  | I |  | 1
Rekonsiliasi Admin API 🔒 (WP-6.10) | A | [6 empty] | R | [5 empty] | C |  |  |  | R |  |  |  | I | C | 1
Language packs & proxy dependensi (P15) | A |  |  | R |  |  | R |  |  | C | C |  |  | C | [8 empty] | C | 1
Evaluasi agent per bahasa & aktivasi D24 (WP-15.10) | C | [11 empty] | R |  |  | R | [5 empty] | A |  | 1
Lingkungan integrasi & kontrak (P16) | A |  |  | R |  |  |  |  | R | R | C |  | C | C | [7 empty] | I |  | 1
Approval aksi R3 di produk (pilot single-owner) | [7 empty] | I | I | [12 empty] | A |  | 1
Cek: jumlah 'A' per baris

## Traceability AC
Traceability AC
AC-01..AC-20 (PRD §12.1) → FR (FR_CATALOG, turunan) → WP pembangun → WP verifikasi E2E. 'Test ada' ≠ AC terpenuhi (bukti E2E/staging belum).
AC | Kriteria | FR terkait | WP pembangun | WP verifikasi | Status
AC-01 | Login/logout; user tanpa hak tidak dapat membuka project user lain | FR-001–007, FR-017, FR-152 | WP-1.1, WP-2.1, WP-1.4 | WP-E2E-01, WP-SEC-01 | Test ada (snapshot)
AC-02 | Project blank/template + import arsip aman | FR-012–016 | WP-1.2, WP-2.1 | WP-E2E-01 | Test ada (snapshot)
AC-03 | IDE baca, cari, tab, edit via workspace API | FR-019–021, FR-026–030, FR-032 | WP-1.2, WP-2.1, WP-2.2 | WP-E2E-01 | Test ada (snapshot)
AC-04 | Prompt → task dengan requirement, plan, status, ID | FR-024, FR-033–034, FR-037–038, FR-048–051, FR-124 | WP-3.2 | WP-E2E-01 | Test ada (snapshot)
AC-05 | Stream progres; reconnect ambil event hilang | FR-035, FR-077, FR-083, FR-145 | WP-3.2, WP-1.4 | WP-E2E-01 | Test ada (snapshot)
AC-06 | Agent hanya memanggil tool yang diizinkan | FR-040–044, FR-059–062, FR-064, FR-067, FR-078–079, FR-117 | WP-3.1 | WP-SEC-01 | Test ada (snapshot)
AC-07 | Kode jalan di sandbox dengan timeout & resource limit | FR-065, FR-068–075, FR-077–078, FR-080, FR-085 | WP-1.3, WP-4.2 | WP-4.3 | Terbukti (komponen), sign-off 🔒 belum
AC-08 | Runner simpan exit code, log, status, durasi, artefak | FR-070, FR-081–092, FR-094 | WP-4.1, WP-1.3 | WP-E2E-01 | Test ada (snapshot)
AC-09 | Diff file/hunk; user dapat menolak patch | FR-029, FR-031, FR-051, FR-095–096, FR-101–102, FR-113–115, FR-120–121 | WP-5.1, WP-5.2 | WP-E2E-01 | Test ada (snapshot)
AC-10 | Code review findings + evidence; reviewer read-only | FR-042–043, FR-097–099 | WP-5.1 | WP-E2E-01 | Test ada (snapshot)
AC-11 | User Proxy status per kriteria + link evidence | FR-039, FR-049, FR-058, FR-092–093, FR-103, FR-105–108, FR-110 | WP-5.1, WP-5.2 | WP-E2E-01 | Test ada (snapshot)
AC-12 | Requirement wajib gagal tidak diterima tanpa waiver | FR-052, FR-058, FR-104, FR-111–112 | WP-5.1 | WP-E2E-01 | Test ada (snapshot)
AC-13 | R3 butuh approval valid; payload berubah → batal | FR-018, FR-043, FR-062–063, FR-067, FR-101, FR-112, FR-118–119, FR-138, FR-141, FR-147 | WP-3.1, WP-INT-03 | WP-SEC-01 | Test ada (snapshot)
AC-14 | Task dapat dibatalkan; sandbox dihentikan | FR-036, FR-052, FR-057, FR-082 | WP-3.2, WP-INT-02 | WP-E2E-02 | Test ada (snapshot)
AC-15 | Secret tidak muncul di frontend/log/artefak | FR-002, FR-025, FR-098, FR-126, FR-128, FR-135, FR-144, FR-158 | WP-1.1, WP-INT-05 | WP-SEC-01 | Sebagian (gap ADR-030)
AC-16 | Token/biaya aktual atau 'unavailable' | FR-011, FR-046, FR-064, FR-131–134, FR-150 | WP-3.1, WP-INT-02 | WP-INT-07 | Test ada (snapshot)
AC-17 | Restart backend tidak menghilangkan task running | FR-010, FR-053–056 | WP-3.2 | WP-E2E-02 | Test ada (snapshot)
AC-18 | Perbaikan gap + revalidasi terbatas | FR-100, FR-104, FR-109 | WP-5.1 | WP-E2E-02 | Test ada (snapshot)
AC-19 | Perubahan punya referensi task & audit | FR-005, FR-009, FR-046–047, FR-066, FR-114, FR-116, FR-143–148, FR-152, FR-154, FR-159 | WP-1.1, WP-2.1 | WP-E2E-03 | Sebagian
AX-01 | Repo privat dapat diimpor lewat GitHub App tanpa token tersimpan di DB/log/.git/config | – (perluasan) | WP-9.1, WP-9.3 | WP-G9 | Belum
AX-02 | Push branch & PR hanya setelah approval R3 terikat head_commit; workflow CI tidak dapat diubah | – (perluasan) | WP-9.4 | WP-G9 | Belum
AX-03 | Webhook dengan tanda tangan salah ditolak; delivery ganda diabaikan | – (perluasan) | WP-9.2 | WP-G9 | Belum
AX-04 | Setiap klaim dari web disertai sitasi + tanggal pencarian; jawaban tanpa sumber diberi label | – (perluasan) | WP-10.3, WP-10.5 | WP-10.6 | Belum
AX-05 | Dokumen PPT/DOCX/XLSX/PDF valid dapat diunduh lewat URL bertanda tangan | – (perluasan) | WP-10.4 | WP-10.6 | Belum
AX-06 | Data berlabel confidential memakai engine lokal; tidak dikirim ke Skills | – (perluasan) | WP-10.4 | WP-G10 | Belum
AX-07 | Generate gambar mematuhi moderasi, kuota, dan menyimpan provenance | – (perluasan) | WP-11.2 | WP-G11 | Belum
AX-08 | Publikasi portfolio memerlukan approval R3 + cek privasi; repo privat hanya metadata terpilih | – (perluasan) | WP-12.2, WP-12.4 | WP-G12 | Belum
AX-09 | AI di portfolio hanya membuat draft bertanda; tidak mengarang pencapaian/testimoni | – (perluasan) | WP-12.1, WP-12.3 | WP-G12 | Belum
AX-10 | Jawaban KB menampilkan sitasi ke potongan dokumen sumber (blok search_result) | FR-168, FR-175–177 | WP-11.3 | WP-G11 | Belum
AX-11 | Router hanya memanggil capability yang aktif & dalam kuota (nonaktif/kuota habis → 0 panggilan provider) | FR-163, FR-165, FR-213–217 | WP-10.1, WP-9.0 | WP-G10 | Belum
AX-12 | Edit manual: buat/edit/rename/hapus file dengan version check; tidak ada overwrite diam-diam; take-over menandai bukti stale & memblokir apply sampai validasi ulang | FR-235–237, FR-244 | WP-13.1 | WP-G13 | Belum
AX-13 | Run, test, dan terminal dari IDE hanya di sandbox dan tersimpan sebagai bukti | FR-239–241 | WP-13.2, WP-13.3 | WP-G13 | Belum
AX-14 | Story ≥ 5 task berjalan paralel; merge queue menguji ulang tiap entri; branch target tidak berisi commit gagal test wajib | FR-221–225, FR-230, FR-254 | WP-13.4, WP-13.5, WP-13.9, WP-13.12 | WP-G13 | Belum
AX-15 | Release dapat ditelusuri requirement → story → task → commit → test → acceptance dan diekspor | FR-222, FR-226, FR-228, FR-231 | WP-13.4, WP-13.6, WP-13.10 | WP-G13 | Belum
AX-16 | Tier M: node executor ditambah tanpa ubah kode domain; node gagal → task dilanjutkan dari checkpoint | FR-245–248, FR-255, FR-258 | WP-13.7 | WP-G13 | Belum
AX-17 | Identitas & tenancy: OIDC (G13); SAML, SCIM ≤ 5 menit, isolasi organisasi, DR drill, SIEM berantai hash (G14) | FR-249–252, FR-256–257 | WP-13.8, WP-14.1..14.5 | WP-G13 (OIDC), WP-G14 | Belum
AX-18 | Repo ≥ 1 juta LOC: index inkremental & pemilihan konteks dalam batas waktu; agent hanya menerima file relevan | FR-253 | WP-13.9, WP-14.7 | WP-G14 | Belum
AX-19 | Setiap panggilan model/vendor tampil di monitoring ≤ 2 dtk dengan token & estimasi biaya; total = ledger; alert budget tepat ambang | FR-283–287, FR-290 | WP-6.9, WP-10.7 | WP-G6 (WP-10.7 → WP-G10) | Belum (prototipe demo)
AX-20 | Rekonsiliasi Admin API: selisih per model per menit/hari; tanpa kredensial berlabel estimasi + alasan; kunci admin tidak keluar dari worker-integrations | FR-288–290, FR-292 | WP-6.10 | WP-G6 | Belum
AX-21 | Setiap pack gelombang 1: template (L1), deps via proxy, build, test, lint, run & package (L1) di sandbox; status test dari laporan nyata | FR-259–264, FR-267–269 | WP-15.0..15.9 | WP-G15 | Belum
AX-22 | Agent lulus set evaluasi per pack L1 di atas ambang PO dengan bukti test | FR-265–266 | WP-15.10 | WP-G15 | Belum
AX-23 | Env ≥ 3 service beda bahasa + DB + broker terisolasi tanpa egress, E2E lulus, teardown otomatis; spec ilegal ditolak | FR-269, FR-271, FR-275, FR-277–280 | WP-16.1, WP-16.3, WP-16.4 | WP-G16 | Belum
AX-24 | Breaking change kontrak memblokir merge queue sampai consumer diperbarui; story lintas service merge setelah contract test + E2E | FR-272–274, FR-276, FR-282 | WP-16.2, WP-16.3 | WP-G16 | Belum
AC-20 | Jalan dari prosedur deployment + health checks | FR-135, FR-137, FR-149 | WP-1.5 | WP-1.6, WP-E2E-03, WP-7.1 | Sebagian

## Status Modul
Status Modul
20 modul PRD §5 → owner agent dan status kode snapshot (integrasi E2E: semua belum).
Modul | Nama | FR | Prioritas | Owner agent | Status kode | Gap utama
M01 | Authentication & User Access | FR-001–006 | P0 | AG-01, AG-04 | Snapshot | SSO fase lanjut
M02 | Dashboard | FR-007–011 | P0 | AG-09, AG-04 | Snapshot | –
M03 | Project Management | FR-012–018 | P0 | AG-09, AG-02, AG-04 | Snapshot | Delete belum membatalkan task aktif
M04 | Repository & Context | FR-019–025 | P0 | AG-09, AG-02 | Snapshot | –
M05 | Browser IDE | FR-026–032 | P0 | AG-09, AG-10 | Snapshot | Uji browser nyata di E2E
M06 | AI Chat Workspace | FR-033–040 | P0 | AG-08, AG-10 | Snapshot | –
M07 | Agent Registry | FR-041–047 | P0/P1 | AG-05, AG-07, AG-04 | Snapshot | Admin UI enable/disable P1
M08 | Orchestrator & Workflow Engine | FR-048–058 | P0 | AG-08, AG-01 | Sebagian | ADR-021/022/024
M09 | Tool Gateway & Policy | FR-059–067 | P0 | AG-07 | Snapshot | ADR-030
M10 | Sandbox & Runtime | FR-068–076 | P0 | AG-03 | Terbukti (komponen) | gVisor belum diuji
M11 | Terminal & Command Runner | FR-077–083 | P0 | AG-03, AG-08, AG-10 | Snapshot | –
M12 | Testing & Debugging | FR-084–094 | P0/P1 | AG-08, AG-10 | Sebagian | E2E browser QA P1
M13 | Diff & Code Review | FR-095–102 | P0 | AG-08, AG-10 | Snapshot | Field author finding
M14 | User Proxy Acceptance | FR-103–112 | P0 | AG-08, AG-07, AG-10 | Snapshot | UI E2E
M15 | Git & Remote Collaboration | FR-113–120 | P0/P2 | AG-02, AG-09 | Sebagian | Remote push/PR P2
M16 | Documentation & Knowledge | FR-121–127 | P1 | AG-09, AG-11 | Sebagian | FR-127
M17 | Provider & Model Settings | FR-128–135 | P0 | AG-07, AG-11 | Sebagian | Readiness gate key nyata
M18 | Deployment & Environments | FR-136–143 | P2 | AG-08, AG-06, AG-11 | Sebagian | Preview routing, production gated
M19 | Observability & Audit | FR-144–151 | P0/P1 | AG-01, AG-09, AG-11 | Sebagian | Dashboard P1
M21 | Portal AI (chat, riset web, dokumen, gambar, KB, analisis) | FR-160–184 (v2) | P1 (inti P10 = P0) | AG-19, AG-20 | Belum | ADR-036..040, 046, 047
M22 | Integrasi GitHub App | FR-185–196 (v2) | P0 (fase P9) | AG-18, AG-10 | Belum | ADR-041, 053, 056
M23 | Portal Portfolio Profesional | FR-197–212 (v2) | P1 | AG-21 | Belum | ADR-042, 056
M24 | Capability Registry & Provider Gateway | FR-213–220 (v2) | P0 (fase P10) | AG-07 | Belum | ADR-037, 044, 050, 051
M25 | SDLC Program & Delivery Management | FR-221–234 (v2.1) | P1 (merge queue & traceability P0ᵉ) | AG-08, AG-09, AG-10, AG-11, AG-14, AG-15, AG-18 | Belum | ADR-057
M26 | Developer Workspace v2 — edit, run, test, debug manual | FR-235–244 (v2.1) | P0ᵉ (FR-235–237); P1/P2 | AG-09, AG-10, AG-03, AG-02 | Belum | ADR-058, 059
M27 | Scale & Enterprise Platform (tier S/M/L) | FR-245–258 (v2.1) | P1 tier M; P2 tier L | AG-06, AG-03, AG-01, AG-02, AG-07, AG-09, AG-11, AG-12 | Belum | ADR-060, 061, 062
M28 | Polyglot Language Packs | FR-259–270 (v2.2) | P1 (L1 = P0ᵉ fase P15) | AG-03, AG-06, AG-09, AG-10, AG-12, AG-15 | Belum | ADR-063, 064, 068
M29 | Lingkungan Integrasi Multi-Service & Kontrak | FR-271–282 (v2.2) | P1 | AG-03, AG-08, AG-09, AG-10, AG-12, AG-15 | Belum | ADR-065, 066
M30 | Monitoring Biaya & Token Realtime | FR-283–292 (v2.2) | P0ᵉ inti; P1 rekonsiliasi | AG-07, AG-11, AG-18, AG-19 | Belum (prototipe demo) | ADR-067
M20 | Admin & Governance | FR-152–159 | P1 | AG-09, AG-11 | Snapshot | –

## Gates
Gates
Gate persetujuan manusia. Agent tidak dapat melewati gate; User Proxy hanya merekomendasikan.
Gate | Titik | Penyetuju | Kriteria lulus | Bukti yang diminta | Status
G0 | Exit Phase 0 | PO | FR_CATALOG disetujui; 9 ADR Proposed diputuskan | Dokumen keputusan PO | Belum
G1 | Exit Phase 1 | PO | Clean install, semua service sehat, migrasi jalan, smoke lulus | Log make up + health | Belum
G2 | Exit Phase 2 | PO | User dapat membuka project dan view/edit file dengan uji otorisasi | Test cross-project + demo | Belum (kode snapshot ada)
G3 | MVP DoD (PRD §13.1) — setelah staging WP-7.1 | PO | Happy path E2E, AC P0 lulus di CI & staging, tanpa temuan kritis, dokumen operator | Laporan E2E + sign-off keamanan + log staging | Belum
G4 🔒 | Security gate sebelum egress internet | PO + AG-13 | Threat T1–T10 terverifikasi, egress allowlist teruji | Sign-off keamanan | Belum
G5 | Exit Phase 5 | PO | E2E membuktikan requirement gagal → perbaikan → revalidasi | Rekaman Playwright AC-18 | Belum
G6 | Exit Phase 6 | PO | Semua P0 + P1 yang disepakati lulus; review biaya & usability pilot; monitoring biaya & token realtime (AX-19, AX-20 bila kredensial ada) | Metrik pilot + E2E monitoring | Belum
G7 | Exit Phase 7 | PO + OPS | Staging dapat diulang; rollback dilatih | Log drill | Belum
G8 | Aktivasi tiap specialist | PO | Manfaat terukur > kompleksitas; contract test & eval set lulus | Laporan eval | Belum
G9 | GitHub end-to-end | PO + AG-13 | Repo privat: import → task → approval → PR; token tidak tersimpan; webhook HMAC teruji | Rekaman E2E + sign-off keamanan | Belum
G10 | Portal AI inti | PO | Evaluasi sitasi & biaya lulus ambang; data-flow per capability terdokumentasi; capability nonaktif/kuota habis tidak memanggil provider (AX-11) | Laporan evaluasi | Belum
G11 | Gambar & analisis | PO + AG-13 | Moderasi & kuota teruji; vendor ADR-040a disetujui; KB bersitasi Recall@8 ≥ 0.85 (AX-10) | Laporan uji vendor + eval KB | Belum
G12 | Portfolio | PO | CV & situs publik dari data nyata pengguna; publish via R3 | Pratinjau + approval | Belum
G13 | SDLC end-to-end tier M | PO + AG-13 | Program kecil end-to-end di tier M; merge queue & traceability; edit/take-over/run/test/terminal; failover node; OIDC | Rekaman E2E + laporan chaos + sign-off keamanan | Belum
G14 | Enterprise tier L | PO + AG-13 | SAML/SCIM, isolasi tenant, microVM, DR drill, SIEM, benchmark repo besar | Laporan uji + DR drill + sign-off keamanan | Belum
G15 | Polyglot language packs gelombang 1 | PO + AG-13 | Matriks test semua pack di CI; deps hanya via proxy; eval per pack L1 ≥ ambang PO; sign-off proxy dependensi | Laporan matriks + eval per bahasa + sign-off keamanan | Belum
G16 | Sistem enterprise terintegrasi multi-bahasa | PO + AG-13 | ≥ 3 service beda bahasa + DB + broker terisolasi tanpa egress; E2E lintas service; breaking change memblokir merge queue | Rekaman env + laporan E2E + sign-off keamanan | Belum
RT | Approval runtime R3 di produk | Pengguna berwenang | Aksi R3 hanya jalan dengan approval terikat payload hash, sekali pakai | Audit event | Desain ✅

## Risiko
Risiko
Risiko PRD §15 (R-xx) + risiko baru dari build Wave 1–2 (RN-xx).
ID | Risiko | Severity | Mitigasi | Pemilik | Status
R-01 | Arbitrary code execution di VPS | Critical | Sandbox profil tetap, socket-proxy, .git mask, limit; gVisor di production | AG-03, AG-13 | Dimitigasi (komponen terbukti)
R-02 | Prompt injection dari repository/log | High | Policy di luar LLM, konten = data, allowlist tool, approval R3 | AG-07, AG-13 | Didesain; uji fixture di WP-SEC-01
R-03 | Agent mengubah file bersamaan | High | Worktree per task, patch atomik, version check | AG-02, AG-08 | Didesain & dibangun
R-04 | LLM mengaku test lulus tanpa bukti | High | Status hanya dari exit code; downgrade evidence User Proxy | AG-08 | Dibangun & teruji
R-05 | Biaya model meningkat karena loop | High | BudgetGuard, batas iterasi/debug/remediasi, kill switch | AG-07 | Dibangun; TASK_MAX_ITERATIONS di WP-INT-01
R-06 | Scope melebar ke 41 agent terlalu awal | High | 6 runtime LLM; 22 agent planned; aktivasi per gate G8 | AG-00, PO | Dikendalikan
R-07 | Kehilangan perubahan pengguna | High | Review-first, expected_sha256, merge tanpa overwrite | AG-02, AG-08 | Dibangun
R-08 | Install dependency butuh network terbuka | Medium/High | Egress proxy allowlist (ADR-007) | AG-03, AG-06 | Desain; WP-6.5
R-09 | Provider tidak mengirim biaya | Medium | cost_status estimated/partial/unavailable | AG-07 | Dibangun
R-10 | Batas resource single VPS | Medium | MAX_ACTIVE_TASKS, pemisahan worker/sandbox (ADR-010) | AG-06 | Didesain
RN-01 | .git/config dari sandbox → eksekusi di host saat git dijalankan worker | Critical | Allowlist config GitAdapter + .git disembunyikan di sandbox (ADR-026) | AG-02, AG-03 | Dimitigasi
RN-02 | Bypass layering via importlib tidak terdeteksi linter | Medium | WorkflowPorts/ToolPorts (ADR-022) | AG-07, AG-08 | Desain; WP-INT-03
RN-03 | SDK Anthropic mencatat prompt di level DEBUG | High | Logger SDK dikunci WARNING; test log | AG-07 | Diperbaiki di snapshot
RN-04 | Transisi state kurang (apply conflict, R3 ditolak, planning) | Medium | ADR-021 | AG-01, AG-08 | Desain; WP-INT-02
RN-05 | Harga model baru belum terpublikasi | Medium | Ditandai verify_before_production; tampil 'estimasi' | AG-07, OPS | Verifikasi di WP-INT-07
RN-06 | Integrasi belum diuji E2E (implementasi dihentikan) | High | Wave 3–4 (AG-12) sebelum klaim MVP | AG-00, PO | Terbuka
RN-07 | Pola redaksi huruf kecil lolos | Medium | ADR-030 | AG-01, AG-13 | Desain; WP-INT-05
RN-09 | Scope melebar 3 portal sebelum IDE stabil | High | Urutan fase P9–P12 hanya setelah G3; gate per fase | AG-00, PO | Terbuka
RN-10 | Kunci GitHub App bocor → akses repo privat | Critical | Secret file read-only, token per operasi ≤1 jam, redaksi ghs_/ghu_, rotasi kunci di RUNBOOK | AG-18, AG-13, OPS | Desain (ADR-041)
RN-11 | Agent Skills tidak tercakup ZDR | High | Engine lokal untuk confidential; tabel data-flow di Settings | AG-19, PO | Desain (ADR-039)
RN-12 | Ekspektasi 'akurat' melebihi kemampuan model | Medium | Sitasi wajib, label tanpa sumber, evaluasi WP-10.6 | AG-19, AG-12 | Desain (ADR-038)
RN-13 | Harga & ketersediaan vendor gambar berubah | Medium | Adapter netral, ADR-040a, kuota & estimasi biaya | AG-19, PO | Desain (ADR-040)
RN-14 | Image toolchain besar (JVM, Android, C++) membebani disk & waktu build (RP-01) | Medium | Cache layer, node executor berdisk besar, pack dipasang sesuai kebutuhan | AG-03, AG-06 | Desain (ADR-063)
RN-15 | Dependency confusion / typosquatting lintas ekosistem (RP-02, T24) | High | Proxy per ekosistem, namespace tunggal, lockfile wajib, deps.audit, D24 | AG-03, AG-13 | Desain (ADR-064)
RN-16 | Lingkungan integrasi jadi jalur lateral movement (RP-03, T25) | High | Network internal per env tanpa egress, tanpa host mount/privileged, image terdaftar, TTL | AG-03, AG-13 | Desain (ADR-065)
RN-17 | Kredensial Admin API bocor = akses admin organisasi (RP-04, T26) | Critical | Opsional, hanya worker-integrations, hanya endpoint usage/cost, redaksi sk-ant-admin, rotasi | AG-07, AG-13, OPS | Desain (ADR-067)
RN-18 | Estimasi biaya menyimpang dari tagihan resmi (RP-05) | Medium | Tarif berversi di PRICING_PATH, rekonsiliasi, label estimasi, alert selisih | AG-07, OPS | Desain (ADR-067)
RN-19 | Scope 13 bahasa sekaligus menurunkan kualitas per bahasa | High | Tingkat L1/L2, eval per pack, aktivasi per pack lewat G8 | AG-00, AG-12, PO | Terbuka
RN-08 | Rate limit Docker Hub / proxy TLS saat build | Low | Mirror registry / cache image, build secret CA | AG-06 | Tercatat